## Slide 1: Annual Work Programme 2010 2nd Draft
Michael Hegarty

## Slide 2: Content
Timeline & inputs
Objectives
Activities in work areas
Summary
  main deliverables
  main MTE related deliverables
  main features

## Slide 3: Timeline and inputs into the AWP 2010
  Additional input for 3rd draft:
  Evaluation Expert Committee meeting
  written MS comments
July
by 30 Oct.
by 30 Dec.
Input for 1st draft
  Needs assessment (2008)
  MTE survey (2009)
  Steering Group
  Missions
  Technical Q’s
  Helpdesk’s TORs
  Additional input for 2nd draft
  Needs assessment (2009)
  TWG Impacts
  Steering Group

## Slide 4: Objectives
Specific objectives
Operational objectives

## Slide 5: Overview activities
3 work areas
Content development
Thematic Working Groups
Thematic pool (desk research, surveys, etc.)
Update of needs assessment
Review of common CMEF indicators
Exchange of information & dissemination
  Glossary, FAQ
  Website,
  Newsletter
  Answers to information request
  Missions to the Member States
  Collaboration with ENRD
Support & guidance
Explanatory notes to the CEQs
MTE assessment tools and guidelines
Training to EC desk officers
Quality Assessment MTE reports
Good practices
Capacity building in the MS through targeted actions
Assessment of evaluation section of Annual Reports

## Slide 6: Thematic Working Group follow-up on impacts of RDPs
  Focus
    Deepen and integrate the outcome of the 2009 TWG on impacts
    Provide specific support to issues raised by MS (e.g. identification of net impact; specific analytical methods, guidance on assessing the overall programme impacts)
  Expected outputs
    Last revision of Guidance Document (Jan. 2010)
    Follow-up guidance for Member States (to be defined)
Content development
Exchange of information & best practice
Support & guidance
Notes: 1.1 To improve evaluation methodology of RD Programmes
The Evaluation Expert Network adopts a thematic approach in order to support the development and improvement of evaluation methods, with a view to contributing to the increase of capacity in the field of evaluation of Rural Development Programmes.
The needs assessment in 2009 has confirmed that the methodological work of the ongoing Thematic Working Groups of 2009 (TWG Impacts; and TWG Leader and Quality of life) is highly relevant. The analysis of the results suggests, that the thematic work on the 7 impact indicators is of ongoing importance for the evaluation stakeholders, although this can be done in various forms of methodological support (e.g. ad-hoc workshops, guidance notes, good practices, technical answers etc.) following the completion of the impacts TWG.
The Thematic Working Group initiated in the second half of 2009, with the aim to streamline methodological approaches for capturing the impact of LEADER and of the measures to improve the quality of life in rural areas, will be completed in 2010.
Aside from these prioritised subject fields, no need has been identified for a new full-fledged Thematic Working Groups as a priority for 2010. The activities of the Helpdesk will concentrate on strengthening the support to the various actors involved in the mid-term evaluation (MTE) process (managing authorities, evaluators, European Commission desk officers) via other types of tools and services (references to the activities below).
A number of topics, which by their nature are not appropriate for being covered by thematic working groups, has been included in the “Thematic Pool”. In 2010, these topics may be tackled by various actions as listed under activity 1.1.5.
1.1.1 Highlight approaches for identifying impacts of specific rural development measures in the context of multiple intervening factors
In order to deepen the outcomes of the 2009 Thematic Working Group “Approaches for assessing the impacts of the rural development programmes in the context of multiple intervening factors”, a set of follow-up activities will be considered (with the possibility of being organised as a Thematic Working Group if appropriate).
1.1.1.1 Follow up on the 2009 work of the Thematic Working Group highlighting approaches for identifying impacts of specific rural development measures in the context of multiple intervening factors (socio-economic and agri-environment)
The work of the Impacts TWG, due to be largely finalised in January 2010, will be concluded following feedback from Member States via the Evaluation Expert Committee meeting (7 December 2009), also incorporating comments from the EC. The finalised Guidance Document will be disseminated at a workshop for Member States’ representatives (subgroup of the Evaluation Expert Committee) in Brussels presumably in March. This event (including the preparation stage) will also be used by the Helpdesk to assess and analyse needs for further/follow-up methodological support which could be provided by the Network from spring 2010.
The follow-up work of the Thematic Working Group will follow the main focus as identified by the Needs Assessment in 2009, e.g.
- providing specific support to issues raised by Member States (e.g. identification of net impact; specific analysis methods etc.)
- providing guidance on assessing the overall programme impacts
The actual methods and tools (which may include one or more of: ad-hoc workshops, guidance notes, good practices, technical answers, etc) will be decided with the EC in an addendum to the Concept concept note in February 2010. This note will be with the ECbased on the feedback from the December meeting and on athe thorough analysis of the needs assessment. After the mMarch meeting the concept note will be fine-tuned..
Expected outputs
 Last revision of Guidance Document on the assessment of socio-economic and environmental impacts of the Rural Development Programmes in the context of multiple intervening factors
 Follow-up guidance for Member States (to be defined) after dissemination of the final Guidance Document

## Slide 7: Thematic Working Group Leader and Quality of Life
  Focus
    Identify methodological approaches for capturing the impact of Leader and QoL measures
    Explore the qualitative and process-oriented nature of Leader effects
    Consider the influence of territorial/local specificities and contexts
  Expected outputs
    Guidance document for the Member States (June 2010)
Content development
Exchange of information & dissemination
Support & guidance
Notes: 1.1.1 Highlight approaches for identifying impacts of specific rural development measures in the context of multiple intervening factors
In order to deepen the outcomes of the 2009 Thematic Working Group “Approaches for assessing the impacts of the rural development programmes in the context of multiple intervening factors”, a set of follow-up activities will be considered (with the possibility of being organised as a Thematic Working Group if appropriate).
1.1.1.1 Follow up on the 2009 work of the Thematic Working Group highlighting approaches for identifying impacts of specific rural development measures in the context of multiple intervening factors (socio-economic and agri-environment)
The work of the Impacts TWG, due to be largely finalised in January 2010, will be concluded following feedback from Member States via the Evaluation Expert Committee meeting (7 December 2009), also incorporating comments from the EC. The finalised Guidance Document will be disseminated at a workshop for Member States’ representatives (subgroup of the Evaluation Expert Committee) in Brussels presumably in March. This event (including the preparation stage) will also be used by the Helpdesk to assess and analyse needs for further/follow-up methodological support which could be provided by the Network from spring 2010.
The follow-up work of the Thematic Working Group will follow the main focus as identified by the Needs Assessment in 2009, e.g.
- providing specific support to issues raised by Member States (e.g. identification of net impact; specific analysis methods etc.)
- providing guidance on assessing the overall programme impacts
The actual methods and tools (which may include one or more of: ad-hoc workshops, guidance notes, good practices, technical answers, etc) will be decided with the EC in an addendum to the Concept concept note in February 2010.
Expected Outputs:
 Last revision of Guidance Document on the assessment of socio-economic and environmental impacts of the Rural Development Programmes in the context of multiple intervening factors
 Follow-up guidance for Member States (to be defined) after dissemination of the final Guidance Document

## Slide 8: Thematic pool
  Suggested themes for further content work of the Helpdesk
    Use of GIS for monitoring and evaluation (experiences from Member States)
    Viable approaches of fostering programme adjustments as a result of ongoing evaluations
    Evaluation of national network programmes, etc.
  Expected outputs
    Support documents, workshop-minutes, thematic papers, explanatory documents
Content development
Exchange of information & best practice
Support & guidance
Notes: Develop further topics from the ‘thematic pool’
A number of topics from the needs assessment have been included in the “Thematic Pool” for the further content work of the Helpdesk. E.g. in 2009 the Helpdesk provided support for developing further the EC’s definition of the result indicator on Gross Value Added in supported holdings/businesses. In 2010, the following topics may still be considered:
- Use of Geographic Information Systems (GIS) for monitoring and evaluation of effects of RD Programmes (experiences from Member States)
- Viable approaches of fostering programme adjustments as a result of ongoing evaluations, etc
- Evaluation of national network programmes
- Adaptations of RD evaluation system due to Health-Check and Economic Recovery Plan
- assessment of qualitative impacts mostly related to axis 3, 4 (e.g improvement in governance)
These topics will not be covered by thematic working groups, but will be tackled e.g. by ad-hoc workshops, quick-surveys, investigations, secondary literature research, collection of good practices etc. The extent of coverage and the most appropriate output will be decided on a case to case basis.
The presented list is not exhaustive and can be amended according to the most urgent needs.

## Slide 9: Update needs assessment, Review common CMEF indicators
  Needs assessment 2011
    Update drawing from all available sources (missions, conferences, focus groups etc.)
  Review common CMEF indicators:
    Identify those indicators that are operating well and those which may require improvements
    Propose solutions in view of possible improvements of the monitoring and evaluation framework for the next programming period
    Exchange with MS
    Draft a discussion paper (Dec. 2010)
Content development
Exchange of information & best practice
Support & guidance
Notes: 1.1.1 Update the assessment of needs carried out in 2010
The paper on the assessment of needs performed in 2009 highlights needs and issues, which will be considered when preparing the successive annual work programmes. However, the exercise on which the paper is based cannot be considered as an exhaustive and final picture of the situation in terms of needs in the field of evaluation of rural development. Due to the evolving nature of the topic, the needs of the evaluation community have to be examined from time to time, drawing from all available sources (Member State Missions, conferences, events), e.g. by means such as national focus groups.
An updated paper will be made available to the Member States and the evaluation community at large: those concerned with the evaluation of Rural Development Programmes will be invited to comment on it. Aspects not taken into account by the paper may also be pinpointed within the framework of contacts established by the Evaluation Helpdesk with Member States, either informally or via missions and events.
Comments and possible additions/amendments will be integrated into the paper.
A similar exercise will be carried out simultaneously with regard to the analysis of evaluation processes (cf. Activity 2.4.1.).
ctivity 1.4.1. - Expected Outputs:
(Cf. Activity 2.4.1)
 Updated paper on the assessment of needs
1.1.2 Prepare the 2011 annual work programme
The aim of this activity is to ensure that the needs identified as part of the assessment organised in 2008 at EU level, and fine-tuned in 2009 through contacts with the Member States and the evaluation community, are addressed in an accurate and consistent manner and encapsulated in a well planned and focused activity schedule.
The following actions are envisaged, which will be run simultaneously:
1.1.2.1 Draft the 2011 annual work programme
The annual work programme will be put together by the Evaluation Helpdesk on the basis of a close collaboration with the European Commission. This action will comprise three key milestones:
- First draft annual work programme compiled and submitted to the European Commission in July 2010
- Second draft annual work programme updated and submitted to the European Commission in October 2010
- 2011 annual work programme finalised and submitted to the European Commission in December 2010.
Timeline:

## Slide 10: Explanatory notes to the common evaluation questions
  Focus
    Further explain the use and purpose of CEQ; definitions of central terms, links between CEQ-criteria-indicators
    Provide examples on format, style and indicative length of answers
  Expected outputs
    Explanatory notes to the CEQ (June 2010)
Content development
Exchange of information & best practice
Support & guidance
Notes: 1.2.3 Develop explanatory notes to the common evaluation questions
In the judgement phase of the MTE the evaluators are asked to answer common evaluation questions (all horizontal, plus those applying to the measures applied in the RDPs) and programme specific evaluation questions and draw conclusions from the analysis regarding the judgement criteria defined in the structuring phase.
However, in the needs assessment, in the Helpdesk’s MTE survey and in some requests for information submitted by evaluators in the Member States it became evident, that special support is needed for this phase of the MTE in 2010. Such support will help to achieve a common understanding and a more consistent approach across all RDPs.
The main needs expressed in the 2009 needs assessment comprise:
- further explanations regarding the use and purpose of Evaluation Questions
- explanation of link between EQ, criteria and indicators
- definition of format, style, indicative length of answers
- support on the meaning of EQ and central terms used in the EQ
- scale problem for answering horizontal EQ (macro-level or programme level)
- clarifications regarding quantitative versus qualitative answers
Providing guidance on these evaluation aspects will help in achieving greater comparability at EU level.
1.1.1.1 Develop Explanatory Notes on Evaluation Questions
This activity is a priority, as it comprises an early step of the MTE (review of Evaluation Questions). While information on the issues to be clarified is available in several documents (CMEF Handbook, MTE Guidance document, technical questions etc.) it will be of important use for the evaluation community to summarize and complete this information in one set of “Explanatory notes”, which can be updated by FAQs.

## Slide 11: MTE-Assessment tools / training
  MTE-Assessment tools and guidelines
    Develop tools and guidelines for DOs to facilitate the assessment of MTE reports
    Develop and disseminate recommendations for MS (June 2010)
  Training to increase the assessment capacity of the DOs
    Conduct a needs assessment among DOs (selected interviews)
    Prepare training material
    Conduct training (autumn 2010)
Content development
Exchange of information & best practice
Support & guidance

## Slide 12: Quality assessment MTE reports
  Focus
    Assessment of a limited number of MTE reports taking into account
      Reliability of data, the methodology
      Soundness of the judgement and conclusions reached
      The overall relevance, quality and comparability of the evaluation reports
  Expected outputs
    Filled quality assessment grid for up to two MTE reports (Dec. 2010)
    Written judgment, including justification, on selected MTE-reports (Dec. 2010)
Content development
Exchange of information & best practice
Support & guidance

## Slide 13: Good practices
  Focus
    Collection/ dissemination of good practices in evaluation methodologies
      i.e. practices in assessing RDP impacts, in identifying the net impact, the use of additional impact indicators etc.
    Collection / dissemination of good practice in evaluation processes
      e.g. cooperation for capacity building in the field of evaluation; activities to improve data quality and reliability for impact measurement; etc.
  Expected outputs
    Set of good practice examples
Content development
Exchange of information & best practice
Support & guidance
Notes: 1.1.1 Identify best practices in terms of evaluation methodology
This ongoing activity aims to provide the European Commission, the Member States and the Evaluation Community at large with examples of good practice worth disseminating and transferring at EU level.
In 2009 a set of good practice examples has been developed and disseminated and used for illustrating the guidance work of the Helpdesk. In the “Synthesis of the annual progress reports for 2007 concerning ongoing evaluation” good practices in the structure of the ongoing evaluation section of the APR, the preparation of the evaluation questions, the tendering of the ongoing evaluators, data management systems have been depicted. In the Working Paper on “Approaches for assessing the impacts of the rural development programmes in the context of multiple intervening factors” practices concerning the application of the PSM method (DID-ATT), methods for the evaluation of the RD agri environmental programme, the estimation of the deadweight loss effects and leverage effects have been collected.
The main focus for 2010 will be
- to collect and prepare good practice examples in a more streamlined manner (e.g. to collect practices relevant for the guidance work of the helpdesk),
- to provide a geographic and thematic balance
- to classify the examples by key words in order to facilitate the website search function,
- to make this information available also on the website of the European Evaluation Network for Rural Development.
This activity is run jointly with Activity 2.2.3. ‘To identify best practice in terms of evaluation processes’. Two actions are envisaged as part of this activity, which aims to:
1.1.1.1 Collect and collate best practice in terms of evaluation methodology
The main source of information for this activity is the expert knowledge within the network as well as the findings of the assessment of the annual progress reports submitted by the Member States in 2010. The examples of good practice are selected according to specific criteria and according to the most urgent needs of the evaluation community.
In 2010 the themes for good practices in evaluation methods will specifically focus on the MTE and indicatively include examples such as:
- practices in assessing RDP impacts
- practices in identifying the net impact
- practices in the use of additional impact indicators (in particular concerning environmental impacts)
- examples of programmes using specific economic models for socio-economic impacts
1.1.1.2 Updating section on “Good practices in terms of evaluation methodology” on website
Based on the collected examples of good practices the set of full descriptions should be further classified (according to key words) and made accessible on the website of the European Evaluation Network for Rural Development on a continuous basis.
The dissemination of these examples of good practice will also be part of the operational objective 3.1. ‘To ensure effective dissemination of information related to evaluation methodology and activities’.
Timeline:
JAN
FEB
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
Activity 1.1.3. - Expected Outputs:
 Set of good practice examples on evaluation methodology (classified by key-words)

## Slide 14: Support of capacity building, Assessment Annual Progress Reports
  Support for capacity building
    through targeted actions (e.g. training material, presentations etc.) in the MS
  Assessment of the ongoing evaluation sections of the APRs submitted in 2010
    Update the assessment template and guidelines
    Assess the functioning of the ongoing evaluation systems in Member States
    Draft a synthesis report
Content development
Exchange of information & best practice
Support & guidance

## Slide 15: Glossary , Frequently Asked Questions
  Glossary
    Update and disseminate trilingual glossary
  FAQ
    Update FAQs based on selected responses to information requests
    Develop own MTE section in FAQ
Content development
Exchange of information & best practice
Support & guidance

## Slide 16: Website, information requests, newsletter
  Website
    Upload of definitive version
    Ongoing update
  Answers to requests for information
    Optimize and speed-up the work-flow
  Newsletter
    3 issues to be published in 2010
Content development
Exchange of information & best practice
Support & guidance

## Slide 17: Collaboration with EC, Member States and ENRD
  Liaise with the EC
    Participate in Steering Group meetings
  Liase with MS
    Evaluation Expert Committee meetings
    Missions to the MS
  Liaise with the ENRD
    European Network for Rural Development and its Contact Point
Content development
Exchange of information & best practice
Support & guidance

## Slide 18: Summary of main deliverables
3 work areas
Content development
Guidance from Thematic Working Groups
Support resulting from the Thematic pool
Needs assessment
Discussion paper on the review of common CMEF indicators
Exchange of information & dissemination
  Glossary, FAQ
  Website
  Newsletters
  Answers to information request
  Missions to the Member States
  Collaboration with ENRD
Support & guidance
Explanatory notes to the CEQs
MTE assessment tools and guidelines
Training (support) material for EC desk officers and MS
Quality Assessment MTE reports and APR
Good practice descriptions

## Slide 19: Summary of main MTE-related* deliverables
3 work areas
Content development
Guidance from Thematic Working Groups*
Support resulting from the Thematic pool*
Needs assessment
Discussion paper on the review of common CMEF indicators
Exchange of information & dissemination
  Glossary, FAQ*
  Website
  Newsletters
  Answers to information request*
  Missions to the Member States
  Collaboration with ENRD
Support & guidance
Explanatory notes to the CEQs*
MTE assessment tools and guidelines*
Training (support) material for EC desk officers and MS*
Quality Assessment MTE reports and APR*
Good practice descriptions*

## Slide 20: Conclusions The AWP 2010 is…
…focusing on the MTE
…deepening the thematic focus
…preparing more tangible results for evaluation stakeholders
…involving evaluators in the Member States to a higher degree
…fostering collaborative forms of work throughout the network
…interlinking existing know-how and increase networking and communication
…raising the visibility of the network

## Slide 21: Thank you for your attention!