GUIDANCE

ON MANAGEMENT VERIFICATIONS

Table of contents

Introduction.................................................................................................................

- General

  - Regulatory requirements

  - General principles and scope of management verifications

- Guidance for Controllers

  - The role of the controllers

  - Guidance for the conduction of verifications

  - Guidance for verifications of public procurement

  - Guidance for verifications of State aid schemes

  - Verifications in the environment  area

  - Equality and non-discrimination

  - Audit trail

- Guidance for beneficiaries

  - The expenditure reporting procedure

  - Supporting documents

  - Guidelines for following the public procurement regulations

Annexes

I.        Control Checklist

II.       Certificate of Verified Expenditure

III.      Table of Expenditure

- First Level Control System of Member States

- Employee’s timesheet for the project

- Employee’s timesheet

# Introduction

The objective of this document is to provide general principles and guidance on the requirements of the verifications the controllers carry out. It covers the regulatory requirements, the general principles and the purpose of verifications and it provides guidance for controllers and beneficiaries. It also provides guidance in specific areas, namely public procurement, aid schemes, environment, the principles of equality and non discrimination and the requirements for audit trail. Furthermore in Annex I the document provides an indicative Control Checklist which is filled in by the controllers. In Annex II it provides the pattern of Certificate of Verified Expenditure which is signed for the expenditure verified. It also provides the Table of Expenditure (Annex III) that the beneficiaries use to submit their expenditure to the controllers who also fill this in. As this document provides general guidance for the first level controllers and the beneficiaries, each Member State could provide more detailed guidance and additional specific questionnaires/checklists incorporating the requirements of the specific national legislative framework.

# 1. general

# 1.1. Regulatory requirements

Under the European Territorial Cooperation objective (ETC), the European Regional Development Fund focuses its assistance on the development of cross-border economic, social and environmental activities, the establishment and development of trans-national cooperation and the reinforcement of the effectiveness of regional policy.

By virtue of Article 15 of Regulation (EC) No 1080/2006 the responsibility for verifying the legality and regularity of the expenditure, under ETC Programmes lies with the participating Member States.

They must set up control systems (systems for verification or first level control systems) and designate controllers who in turn carry out the verification of the legality and regularity of the expenditure declared by each beneficiary participating in the operation. The Managing Authority shall satisfy itself that the expenditure of each beneficiary participating in an operation has been verified by the controller referred to in Article 16(1) of Regulation (EC) No 1080/2006.

In order to verify the expenditure, pursuant to Article 16 of Regulation (EC) No 1080/2006, each Member State shall set up a control system making it possible to verify the delivery of the products and services co-financed, the soundness of the expenditure declared for operations or parts of operations implemented on its territory, and the compliance of such expenditure and of related operations, or parts of those operations, with Community rules and its national rules.

For this purpose each Member State shall designate the controllers responsible for verifying the legality and regularity of the expenditure declared by each beneficiary participating in the operation.

Member States may decide to designate a single controller for the whole programme area. Where the delivery of the products and services co-financed can be verified only in respect of the entire operation, the verification shall be performed by the controller of the Member State where the lead beneficiary is located or by the Managing Authority.

Depending on the Member State a centralised or a decentralised system can be selected. The first level control system is described on the approved documents of the First Level Control System of each Member State which are attached in Annex IV and published in the website of the Managing Authority of the Programme.

# 1.2 GENERAL PRINCIPLES AND scope of management verifications

According to Article 13(2) of EC 1828/2006 verifications or management verifications comprise two important procedures namely, administrative verifications (desk-based verifications) in respect of each application for reimbursement by beneficiaries and on the-spot verifications of individual operations. Administrative verifications, which apply to 100% of the declared expenditure, are not sufficient on their own to give assurance on all elements concerning the legality and regularity of the expenditure and it is therefore essential that on-the-spot verifications are carried out in order to check in particular the reality of the operation, that the delivery of the product/service is in full compliance with the terms and references of the Subsidy Contract, that the beneficiary’s Table of Expenditure is correct and that the actions and expenditure are in line with the community and the national rules.

All applications for reimbursement by beneficiaries, whether intermediate or final applications, should be subject to administrative verifications based on an examination of the claim and relevant supporting documentation such as invoices, delivery notes, bank statements, progress reports and timesheets.

Each Member State could further specify the supporting documents and the required documents that beneficiaries must submit, as described in Chapter 3.

The administrative verifications should check:

- The correctness of the application for reimbursement.

- That expenditure relates to the eligible period.

- That the expenditure relates to an approved operation.

- Compliance with programme conditions.

- Compliance with the approved financing rate, where applicable.

- Compliance with national and Community eligibility rules.

- Adequacy of supporting documents and of the existence of an adequate audit trail.

- Compliance with State aid rules, environmental rules and equal opportunity and non discrimination requirements.

- Compliance with EC and national public procurement rules.

- The respect of EC and national rules on publicity.

It is necessary to carry out on the spot verifications in order to verify that the project is actually realised and that there is full compliance of the deliverables, products or/and services, with the terms of the Subsidy Contract. The economic and physical progress of the project, the compliance of the community rules on publicity, the accuracy of the data the beneficiary provides in the progress report and the audit trail are verified.

The methodology used by controllers for carrying out Article 13(2) of Regulation 1828/2006 verifications should be set out in the procedures manuals of each body identifying which points are checked in the administrative verifications and in the on-the-spot verifications respectively and referring to the checklists to be used for the different checks executed.

On-the-spot verifications are carried out on a sample basis. Where sampling is used the controller shall keep records describing and justifying the sampling method and a record of the transactions or operations selected for verification. The controllers shall determine the size of the sample in order to achieve reasonable assurance as to the legality and regularity of the underlying transactions, having regard to the level of risk identified by the Managing Authority for the type of beneficiaries and operations concerned. The selected sampling method must be justified. It is reviewed each year and it should be reported on the periodic (semester) reports to the Managing Authority. Following guidelines from the Managing Authority, in the periodic reports, all the required information for the verification of expenditure (number of on the spot verifications in the reporting period and relevant conclusions) shall be reported and particular emphasis will be given to the irregularities detected.

The sampling method adopted for on-the-spot-verifications will be based on risk factors such as:

- size of the project (type of project, budget);

- size of the partnership;

- type of beneficiary (legal entity and organisational type);

- number of projects implemented by the beneficiary;

- type of eligible expenditure;

- inclusion of private bodies in the partnership;

- comparison of works planned and realized (taking account of implementation delays);

- indication of management problems;

Due to the nature of the verifications foreseen, both lead beneficiaries and beneficiaries will be covered by these.

As good practice it is recommended that the controller or the body monitoring the controller be appointed from the beginning of the project in order to have consulting role for public procurement issues (preventive control) and in particular to prevent irregularities.

Documenting management verifications

All management verifications should be documented. The records should state the work performed, the date of the verification, and the results of it.

In case irregularities are detected prior to the verification of expenditure by the controller, the controller, taking into consideration the type and the nature of the irregularity, could proceed to recommendations. The beneficiary shall comply within the set deadline according to the recommendations sent. The beneficiary’s compliance with the recommendation is verified by the controller at a later verification, administrative or on the spot. In case there are recommendations these are communicated to the beneficiary as well as to the lead beneficiary and the Managing Authority.

In case there is no compliance the controller informs in written the Managing Authority and the responsible National Authority of the Member State where the beneficiary is based.

Checklists, which act as a guide for carrying out the verifications should be sufficiently detailed. A list of each of the eligibility points verified should be detailed with the respective documentation (e.g. conformity of supporting documents and bank statements, appropriate and reasonable allocation of overheads to the operation). The name of the controller performing the verifications and the date they were carried out should always be recorded. Photographs of billboards, copies of promotional brochures, training course materials, diplomas provided etc provide evidence of the compliance of the project with the publicity requirements of the Programme. An indicative Control Checklist with the minimum requirements is attached in Annex I.

# 2. Guidance for controllers

# 2.1. THE ROLE OF THE CONTROLLER

Article 13(2) of Regulation (EC) No 1828/2006 requires that the verifications to be carried out by the controllers under Article 60(b) of Regulation (EC) No 1083/2006 shall cover administrative, financial, technical and physical aspects of operations, as appropriate.

Verifications shall ensure that the expenditure declared is real, that it is linked to the project, that the products or services have been delivered in accordance with the Subsidy Contract, that the applications for reimbursement by the beneficiary are correct and that the operations and expenditure comply with Community and national rules. They shall include procedures to avoid double-financing of expenditure with other Community or national schemes and with other programming periods.

The controllers must verify that the co-financed products and services have been delivered and that the expenditure declared by beneficiaries for operations has actually been incurred and complies with Community and national rules.

For this purpose they perform administrative verifications in respect of each application for reimbursement by beneficiaries and on-the-spot verifications of individual operations, which could be carried out on a sample basis. Furthermore, the controllers should verify that beneficiaries involved in the implementation of operations maintain either a separate accounting system or accounting code for all transactions relating to the operation. Project beneficiaries should hence always refer to national guidelines to make sure that the respective expenses are eligible.

First Level Controllers shall:

- verify the expenditure incurred by the controlled beneficiaries;

- verify the content of both the activities and the finances of the beneficiary report, collecting and assessing the available/provided data and/or carrying out interviews for clarification or completion of the data with additional data

- draft the checklist on the verification carried out (an example of checklist has been included in Annex I)

- sign a declaration of the validation of expenditure named Certificate of Verified Expenditure (the pattern is attached in Annex II)

- report potential findings in detail.

By signing the Certificate of Verified expenditure the controller of each beneficiary verifies all requested documents and declares the proper use of funds. This statement should be based on proper checks. The controller is responsible for the methods and techniques of the control in accordance with national control regulations. For expenditure not verified or if there is recommendation there should be relevant justification, with explicit reference to the provisions not respected.

Each Member State may provide more detailed questionnaires/checklists than the attached, taking into account the specifications of national legislative framework.

Carrying out the verification the controllers shall take into account:

- Programme documents, e.g. the Call for proposals, the Programme Manual, the Memorandum of Understanding (where available), the website of the Programme and /or other documents setting out the requirements for first level control.

- Data on the project, e.g. the approved application form and possible amendments, the Subsidy Contract, the Partnership Agreement etc

- Data on the Management and Control System

- Data on legislation, regarding the beneficiary, e.g. the implemented national law and the beneficiary’s regulations

- Data on the beneficiary and the project, e.g. beneficiary’s procedure, previous certifications etc

- National rules on competition, state aid and public procurement

• Community documents e.g.:

- Council Regulation (EC) No 1083/2006 of 11 July 2006 laying down general provisions on the European Regional Development Fund, the European Social Fund and the Cohesion Fund and repealing Regulation (EC) No 1260/1999

- Council Regulation (EC) No 1341/2008 of 18 December 2008 amending Regulation (EC) No 1083/2006 laying down general provisions on the European Regional Development Fund, the European Social Fund and the Cohesion Fund, in respect of certain revenue-generating projects

- Council Regulation (EC) No 284/2009 of 7 April 2009 amending Regulation (EC) No 1083/2006 laying down general provisions on the European Regional Development Fund, the European Social Fund and the Cohesion Fund concerning certain provisions relating to financial management

- Regulation (EC) No 1080/2006 of the European Parliament and of the Council of 5 July 2006 on the European Regional Development Fund and repealing Regulation (EC) No 1783/1999

- Regulation (EC) No 397/2009 of the European Parliament and of the Council of 6 May 2009 amending Regulation (EC) No1080/2006 on the European Regional Development Fund as regards the eligibility of energy efficiency and renewable energy investments in housing

- Commission Regulation (EC) No 1828/2006 of 8 December 2006 setting out rules for the implementation of Council Regulation (EC) No 1083/2006 laying down general provisions on the European Regional Development Fund, the European Social Fund and the Cohesion Fund and of Regulation (EC) No 1080/2006 of the European Parliament and of the Council on the European Regional Development Fund

- Commission Regulation (EC) No 846/2009 of 1 September 2009 amending Regulation (EC) No 1828/2006 setting out rules for the implementation of Council Regulation (EC) No 1083/2006 laying down general provisions on the European Regional Development Fund, the European Social Fund and the Cohesion Fund and of Regulation (EC) No 1080/2006 of the European Parliament and of the Council on the European Regional Development Fund

- Directive 2004/18/EC of the European Parliament and of the Council of 31 March 2004 on the coordination of procedures for the award of public works contracts, public supply contracts and public service contracts

- The commission interpretative communication (2006/C179/02) on the Community law applicable to contract awards not or not fully subject to the provisions of the public procurement directives.

In case the verification concerns the lead beneficiary, the controller shall examine how the lead beneficiary ensures that the expenditure of the beneficiary has been verified by the controller and that the work has been realised and the respective deliverables been accepted according to the Subsidy Contract.

When part of an operation is implemented outside the European Community or outside of the territory of the participating Member States (according to article 21 of Regulation 1080/2006) the controller of the beneficiary of which the proposal contains the expenditure, has the responsibility for the legality and regularity of it.

# 2.2 Guidance for carrying out verifications

The controller, during the examination of the data submitted by the beneficiary, examines mainly the completeness of the data submitted according to the attached Control Checklist.

1. During the control of completeness it is examined whether:

- the pattern of Table of Expenditure has been submitted

- the supporting documents have been submitted

- the Subsidy Contract and the approved application form have been submitted

- the Partnership Agreement has been submitted

- the implementing body is the same as the beneficiary of the approved application form. If the implementing body is not the same as the beneficiary of the approved application form it is examined whether there is a Programming Contract acceptable by the rules of the Programme. In case expenditure has been realized by a body different from the body of the approved application form, through a Programming Contract, this procedure shall be in accordance with the procedures of the Programme

- the regulatory framework in force, setting out the operation of the beneficiary has been submitted

- the legislation the beneficiary follows to recruit temporary staff or to pay his staff additional remuneration has been submitted

Following, he proceeds to the examination of the data according to the specific issues described:

2. Compliance of the expenditure with the project- Realisation of the expenditure

For the compliance of the expenditure with the project the following are examined:

- Whether the declared expenditure is described in the approved application form as respective category of expenditure. If a relevant category of expenditure has not been approved the necessary documents, as in the Programme Manual, shall be provided.

- Whether the declared expenditure is eligible within the framework of the declared category. If it is not eligible then it is removed to the corresponding category of expenditure.

- Whether the categories of eligible expenditure per beneficiary have been respected.

- Whether the expenditure has been properly allocated to the work package and the respective category of eligible expenditure.

The controller also examines whether there is available budget on the specific category of expenditure, taking into consideration the approved budget of the project and the expenditure that has already been verified in the specific category of expenditure. If there is no available budget, he/she examines whether the expenditure can be verified within the flexibility rule of the Programme, regarding the transfer of budget between categories of expenditure as specified in the Programme Manual.

In any case the lead beneficiary shall be informed and to conform.

If finally the remaining budget in category of expenditure is not sufficient, then only the expenditure of the remaining budget is verified.

In order to verify the realization of the expenditure the following are taken into consideration:

- The existence of the foreseen supporting documents from the respective legislative framework of the Member State, e.g. invoices, dispatch notes, discharge notes, payrolls, checks, bank extraits, bank deposits, remittances and other bank documents verifying that the expenditure has been realized and paid (reservation on depreciation). Expenditure not accompanied by the supporting document is not verified.

- In case expenditure is paid in cash, accounting data from the cash register and the cash movement shall be provided.

The following are further examined:

- Whether the expenditure has been realized outside the eligible period as specified in the Subsidy Contract. If there are different dates for the eligibility of the physical and economic work of the project it is examined based on these.

- Whether the expenditure has been realized within the reporting period for verification. If the expenditure was realized during previous period, it is verified if it was not included in the previous requests for verification.

- If there are deliverables for the respective expenditure and in particular:

a) the existence of the deliverables or parts of the deliverables, the implementation of which is the responsibility of the beneficiary according to the Subsidy Contract and/or other documents of the project (e.g. minutes) is verified

b) the existence of certificates of acceptance and the certificate of acceptance of the deliverable from the lead beneficiary or from the responsible of the deliverable where the part of the deliverable produced by the beneficiary adds, is verified.

The deliverables are produced by the beneficiary either in house or by award to third party. Accordingly the verification of personnel costs is linked to the certification of the deliverables.

In case the controller is required to verify expenditure where there is no deliverable, e.g. in interim payments to third parties or personnel cost, data from which the declared man-hours are derived, e.g. draft deliverables and/or certificate from the lead beneficiary that the declared man-hours of the beneficiary is according to the physical progress of the project that the beneficiary is in charge, are required.

Expenditure that corresponds to uncompleted deliverable, e.g. cost for setting up or updating a website that is not operational and up to date, cost for non operational or non functional equipment etc is verified, provided that the completion of the deliverable is certified when the project is completed.

Expenditure of a deliverable that can be verified in another Member State is verified after the deliverable is certified by the first level control system of the other Member State and the certificate of acceptance is sent, e.g. verification of shared costs.

- Whether the eligibility rules on VAT, penalties and financial penalties have been properly applied. VAT is eligible if there is no revenue for the beneficiary at the implementation of the project or following the completion of the project and are linked to it, or if there is revenue this is for a non taxed activity. In any case if VAT is returned or offset it is not eligible.

3. Accounting report of the expenditure

It is examined whether all expenditure is recorded coded at the accounting system of the beneficiary, in order to be recognisable either in a separate accounting system or there is sufficient accounting coding subject to national accounting rules. Expenditure that is not registered in the accounting unit of the project is not verified, except if the recording is not possible, e.g. general costs, personnel cost etc.

4. No double funding of the declared expenditure

The control aims to ensure that the declared expenditure is not funded or has not been funded by other national or community source, according to article 13 (2) EC Regulation 1828/2006. In order to verify that there is no double funding:

- the original documents issued shall bear a stamp with the acronym of the project, the programme and in case of shared expenditure the eligible amount. In case of depreciation cost a copy of the invoice of the purchase and the accounting registration in the accounting books shall be provided.

- the expenditure shall be registered in a separate, for the project, accounting unit

- the public contracts of the project shall mention the acronym and the Programme.

5. Eligible cost

5.1 Personnel cost

It is examined whether the expenditure is regarding personnel that worked for activities of the project and the amount that corresponds to that work. For the documentation of expenditure of the co funded project paid for personnel cost, the following are examined:

- Whether there is a decision of the beneficiary’s management which specifies the working team, including specific reference to the staff who will work for the project, the division of work, the allocation of working hours, the project manager and the person in charge for accepting the activities/deliverables. The aforementioned could be replaced by employment/labour contracts for each member of the working team which are approved and signed by the responsible body or person according to the institutional framework of the body.

- Whether there are employment/labour contracts and data on the selection procedure (e.g. Call, candidates, evaluation, decisions etc) when staff have been hired for the project.

- Whether there are decisions of the management regarding the recruitment of staff with reference to the relevant legislation that specifies the recruitment process.

- The existence of monthly timesheets, Annex V, which present the actual hours worked, the venue of the work and the nature of the work per employee. These should me signed by the employee, the beneficiary’s responsible and the responsible of the activity.

- Data on the total hours worked per month and date, per each employee working on the project, Annex VI, broken down to all the co funded activities/projects he/she has been involved. These are submitted at the end of the value period in printed and electronic version, signed by the employee and validated by the beneficiary’s legal representative. The calculation of the cost of the shared personnel is conducted based on the actual total time of employment and the total personnel cost of the beneficiary.

- Reports on the produced, by the staff, work during the respective period. The reports should be verified by the responsible of the activity.

- Signed payrolls or payslips or proofs of bank deposits or other supporting documents.

5.2 Travel and accommodation

It is examined whether the expenditure is linked to the project, if it is in the approved application form as well as its level and the way it has been paid. For the documentation of expenditure of co funded project paid for travel and accommodation the following are examined:

- Invitation and/or minutes, presenting the time, duration, venue as well as signed list of participants for all the days of the meetings.

- Decision for travelling according to the institutional framework of the beneficiary.

- Travel report/Report on the travel expenditure according to the institutional framework of the beneficiary.

- The beneficiary’s regulation on the level of the subsistence allowances, the kilometre allowance for using private car.

- Tickets, invoices of tickets and supporting documents for payment of tickets, toll invoices, invoices when using taxi or when renting a car or kilometre allowance when using private car. In case of travelling by plane, boarding pass is also required.

- The use of taxi or the rent of a car shall be justified either because there is no public transport (including strikes etc) or the beneficiary is travelling to subsequent destinations or it is the most economic way of travelling. In case of insufficient justification the value of travelling by the most economic mean is paid.

- Hotel invoices and supporting documents for hotel payment only for their stay (room service is not included) and for those travelling who should be mentioned in the hotel invoice by name. In case voucher is issued a copy of it should be submitted with the travel agency invoice.

Cost for travelling and accommodation of external experts is paid according to the aforementioned rules only when this is explicitly included in their contracts.

- Subsistence allowances (only for staff) according to the institutional framework of the beneficiary.

- When field work or similar activities are foreseen, these should be explicitly described in the approved application form and prior to their commencement the beneficiary shall approve a total plan (programme) for this purpose. In any case the results of the field work should be kept and should be attached to the travel report.

- In case of travelling outside the eligibility area of the Programme the decisions of the approved bodies of the Programme justifying these trips.

- In case partners or participants from countries outside the EU travel to the eligible area of the Programme in order to participate to events, justification from the responsible person of the beneficiary or the responsible person of the activity for their participation.

In case of public procurement for the organisation of workshops, conferences, meetings etc the following are also examined:

- Photographs in case of workshops, conferences etc.

- Contracts and documents for the award procedure (call, tenders, evaluation, decision etc)

- Invoices which should state the project and the Programme

- Certificate of acceptance of products and services

- Documents of payment

The publicity and information documents that address the general public shall respect the rules on publicity of Regulation 1828/2006 (community emblem, Programme logo, co funding from ERDF)

5.3 Publication, information, promotion

It is examined whether the expenditure is linked to the project, if it is in the approved application form as well as its level and the way it has been paid. For the documentation of expenditure of co funded project paid for publication, information and promotion the following are examined:

- Contracts and documents for the award procedure (call, tenders, evaluation, decision etc)

- Certificate of acceptance of products and services

- Invoices and dispatch notes which should state the project and the Programme

- Documents of payment

- Deliverables of the services offered

- Website of the Programme

- Invitation and agenda

- Minutes

- Singed list of participants

- Photographs of the events

The publicity and information documents that address the general public shall respect the rules on publicity of Regulation 1828/2006 (community emblem, Programme logo, co funding from ERDF)

5.4 Equipment and depreciation

It is examined whether the expenditure is linked to the project, if it is in the approved application form as well as its level and the way it has been paid. It is also examined whether the expenditure is for the total purchase value of the equipment or its depreciation and the way the depreciation has been calculated. The time of purchase of the equipment in relation to the implementation stage of the project, the cost break down in the project and whether the equipment is set and operational are also examined. For the documentation of expenditure of co funded projects paid for equipment the following are examined:

- Contracts and documents for the award procedure (call, tenders, evaluation, decision etc)

- Certificate of acceptance of products

- Registration of the equipment in the accounting system

- Invoices and dispatch notes with reference to the Serial Number of the equipment.

- Documents of payment

- Licenses to set and operate the equipment, where required.

In addition to the aforementioned for the documentation of depreciation the following are examined:

- Documentation of the method for depreciation according to the national accounting rules

- Method for partitioning the use of the equipment in the project

5.5 External experts

It is examined whether the expenditure is linked to the project, if it is in the approved application form as well as its level and the way it has been paid.. For the documentation of expenditure of co funded project paid for external experts the following are examined:

- Contracts and documents for the award procedure (call, tenders, evaluation, decision etc)

- Receipts of invoices which state the project

- Deliverables and certificate of acceptance of deliverables

- Documents of payment

5.6 Preparation cost

In case of verifying preparation cost the special eligibility rules as set out in the Programme documents, e.g. Call for proposals etc, shall be taken into account. Preparation cost is eligible if it has been realised between 1 January 2007 and the date of approval of the Application Form.

5.7 Overheads

It is examined whether the expenditure is linked to the project, if it is in the approved application form as well as its level and the way it has been paid. The method breaking down indirect costs is also examined. For the documentation of expenditure of co funded project paid for overheads the following are examined:

- invoices, receipts and documents of payment.

- description of the methodology and the basis for allocation of overheads (where required)

5.8 Public goods and services

It is examined whether the expenditure is linked to the project, if it is in the approved application form as well as its level and the way it has been paid. It is also examined whether the required studies and licenses have been submitted. For the documentation of expenditure of co funded project paid for public goods and services the following are examined:

- Contracts and documents for the award procedure (call, tenders, evaluation, decision etc)

- Certificate of acceptance of products

- Invoices, contractor’s accounts, summary tables of works

- Documents of payment

- The required by the national legislation on environment licenses, the license to set and operate equipment (where required)

- In case of public projects implemented in house, diary of works.

5.9 Other expenditure

It is examined whether the expenditure is linked to the project, if it is in the approved application form as well as its level and the way it has been paid, e.g. expenditure for managing, monitoring and controlling the project, leasing, bank fees, guarantees etc.

6. Compliance with the public procurement rules

The beneficiary’s compliance with the provisions of the community and national legislation on public procurement rules is examined. Specific guidelines are provided in Chapter 2.3.

7. Compliance with the community policies

The existence of the required, by the community and national legislation in force, studies and licenses is examined. In case these are not available the expenditure is not verified. The control takes into account the provisions foreseen in the project and the relevant legislation on state aid, environment, the principles of equality and non discrimination according to the specific guidance provided in Chapters 2.4, 2.5 and 2.6.

8. Respect of the community rules on publicity in all documents and deliverables of the beneficiary

The controller examines the respect of the provisions of the Regulations on the ERDF and the Programme publicity rules. It is examined whether all deliverables and all documents bear in a visible part the project logo, the Programme logo, the ERDF co funding and the Community emblem, according to the Programme provisions and the provisions of Regulation 1828/2006.

9. Other controls

Control of project revenue according to article 55 or Regulation 1083/2006 as in force.

The controller examines the generation of revenue from the management of the deliverables. A project generating revenue means any operation involving an investment in infrastructure the use of which is subject to changes borne directly by users or any operation involving the sale or rent of land or buildings or any other provision of services against payment, irrespectively of who receives the revenue, the beneficiary or a third party. The state aid projects are exempted.

In case of projects generating revenues in the implementation stage, these are declared separately in every request for verification of expenditure of the beneficiary. In case there is revenue, a cost benefit study, using the “Guide to cost benefit analysis of investment projects” published by DG Regio in 2008, shall be attached to the Application form.

In case prior estimation of revenues is not feasible, the revenues generated in the implementation stage and five years following the completion of the project are excluded from the expenditure declared to the European Commission.

# 2.3 guidelines for verifications of public procurement

Verifications in relation to public procurement should aim to ensure that EC public procurement rules and related national rules are complied with and that the principles of equal treatment, non discrimination, transparency, free movement and competition have been respected throughout the entire process.

Chapter 3 provides specific guidance on public procurement to be used by beneficiaries. This is particularly useful where beneficiaries are involved in ‘one-off’ contracts and lack relevant experience. Guides and explanatory notes on the Community rules for public procurement have been produced by the European Commission and provide useful information and explanations. (http://ec.europa.eu/internal_market/publicprocurement/index_en.htm)

In cases of public contracts particular attention should be paid by controllers to checking:

- The appropriateness of the procurement method being used;

- The compliance of the principles of transparency, non-discrimination, equal treatment and effective competition;

- The interdependence between the different contract phases;

- That appropriate selection and award criteria have been used.

Although there are specific publicity requirements required by EC public procurement rules, even where contracts fall below the EC thresholds or where services are subject only to a limited application of Directive 2004/18/EC (i.e. Annex IIB) or of Directive 2004/17/EC (i.e. Annex XVII B), an adequate (i.e. in the context of the size and nature of the contract12) level of publicity of the contract should be respected.

Particular areas of the tender evaluation and award procedures where Member States may provide specific guidance to beneficiaries include:

- compliance with the advertising procedures, sufficient degree of advertising

- compliance with the fundamental principles of the EC Treaty (transparency, non-discrimination, equal treatment

- separation between the selection phase and award phase of the procedure

- correct application of selection criteria and award criteria

- modifications of the contract award at implementation stage which have no substantial impact

- in house contracts.

# 2.4 guidelines for verifications of State aid schemes

Aid schemes may pose problems as regards management verifications due to the following:

- increased control risk (i.e. the inherent complexity of the rules governing the aid scheme, the nature of those recipients – i.e. SMEs – with the risk of a potentially weaker control environment etc.);

- specific eligibility criteria;

- specific provisions concerning the final date of eligibility of expenditure.

There are several key risk areas which should be checked by management verifications in the area of State aid, namely:

- that the aid scheme has been notified to and approved by the Commission or that it is covered by either a block exemption or satisfies the de minimis rules  whereby the aid scheme does not need to be notified;

- that the undertakings in receipt of the aid satisfy the conditions of the aid scheme as approved by the Commission or that the nature of the operations covered by a block exemption satisfy the particular exemption conditions;

- that there is no overlapping of aid from different sources which could breach the de minimis rule or the applicable rules on the cumulation of aid. The ceiling for the aid covered by the de minimis rule is in general €200,000 over any 3 year fiscal year period and for activity in the road transport sector is €100.000.

In any case the state aid shall be in accordance with Regulation 1998/2006 as in force.

The Directorate General for Competition has issued a useful guide and fact sheets on the Community rules on State Aid (http://ec.europa.eu/competition/state_aid/studies_reports/vademecum_on_rules_09_2008_en.pdf  and guidelines on national regional aid 2007-2013 (2006/C54/08)

# 2.5 verifications in the environment area

Verifications in the environment area should, where relevant, verify that the beneficiary has complied with the relevant Directives by checking whether the relevant consents have been obtained from the competent national authorities in accordance with the applicable procedures. The competent national authorities are responsible for ensuring that EC environmental legislation is correctly applied, and for taking appropriate steps accordingly if this is not the case.

# 2.6 Equality and non-discrimination

Pursuant to Article 16 of Regulation (EC) No 1083/2006 verifications should check that operations respect and promote equality between men and women and that the integration of the gender perspective has been applied during the various stages of implementation of the Funds. This involves a gender mainstreaming approach ensuring that all measures and operations openly and actively take into account their effects on the respective situation of women and men, with a view to overcoming inequalities. All programmes and operations should contribute to improved equality between men and women, and should be able to demonstrate this impact in this respect, prior to, during and after implementation. In addition, verifications should also check that appropriate steps have been taken to prevent any discrimination based on sex, racial or ethnic origin, religion or belief, disability, age or sexual orientation during the various stages of implementation of the Funds and, in particular, in the access to them. Checklists used for management verifications should therefore, where relevant, include questions dealing with the respect of the principles of equality and non-discrimination. Management verifications should check the actual performance of co-financed measures against the target indicators included in the operational programme throughout the programming period.

# 2.7 AUDIT TRAIL

At the Joint Technical Secretariat/Managing Authority the following documentation shall be held:

a) The decisions of the Monitoring Committee referring to the approval of the project selection criteria and of the material related to the call for proposals, the Application Forms submitted by the potential beneficiaries, the evaluation assessment forms filled in by the Joint Technical Secretariat and the decisions regarding the approval of the projects. For the selected projects, the JTS/MA maintains the Subsidy Contracts and the Partnership Agreements.

b) All documentation relevant to the implementation of projects (progress and financial reports, any other reporting documents submitted by the lead beneficiaries supporting the request for reimbursement and documents proving the payment transfer from the Paying Authority of the CFS, the Community Initiatives and the Cohesion Fund to the lead beneficiaries).

The lead beneficiary keeps a full file of the project (Subsidy Contract, Partnership Agreement, relevant documents of the verified expenditure of the beneficiaries, copies of the receipts of each beneficiary) as well as the documents proving the transfer of the payment to the beneficiaries. It is the lead beneficiary’s responsibility to ensure an adequate audit trail which implies that the lead beneficiary has an overview of:

• Who paid

• What was paid

• The date on which payment was made

• The person who carried out the verifications

• The location where the relevant documents are stored.

The lead beneficiary must ensure that all beneficiaries keep the documents linked to the project in an ordered and safe way until 31 December 2020, if not longer, in case national regulations require a longer period for filing. The filed documents can be either the originals or the certified as original copies on commonly used data media (in accordance with national legislations).

Each beneficiary keeps all data regarding the legal commitments of the part of the project he has to implement: terms of reference, call for tender, proof of publication, decision of the evaluation committee, contracts and annexes (technical requirements), financial plan, deliverables, payment proofs and other accounting documents, all documents related to the verification carried out by the controller and the documents that he has sent to the Lead beneficiary and the MA/JTS). Each beneficiary must ensure that all accounting documents linked to the project are available and that they are filed separately.

- The following at least shall be considered as commonly accepted data:

(a)	photocopies of original documents;	

(b)	microfiches of original documents;	

(c)	electronic versions of original documents;	

(d)	documents existing in electronic version only.

The procedure for certification of conformity of documents held on commonly accepted data carriers with the original document shall be laid down by the national authorities and shall ensure that the versions held comply with national legal requirements and can be relied on for audit purposes. Where documents exist in electronic version only, the computer systems used must meet accepted security standards that ensure that the documents held comply with national legal requirements and can be relied on for audit purposes.

# 3 guidance for beneficiaries

# 3.1 The expenditure reporting procedure

The lead beneficiary submits to the Joint Technical Secretariat (JTS) progress reports on project implementation activities in accordance with the timetable referred to in the approved Application Form and the Programme Manual as in force.

Payment requests for project expenditure actually made will derive from the relevant reporting period progress reports consisting of an activities report and a financial report. Prior to filling in a progress report, the lead beneficiary will collect the expenditure made by all beneficiaries including itself, which must be accompanied by the relevant verifications signed by the competent controller of the respective country. The verified expenditure of all beneficiaries must be attached to the relevant progress reports. The lead beneficiary will use the official forms (Progress Reports) as in force, which are provided by the MA.

Should the beneficiaries delay in submitting to the lead beneficiary their activity and financial reports, the lead beneficiary will still abide by the deadlines for submission. Should the beneficiaries delay in submitting to the lead beneficiary their Table of Expenditure, the lead beneficiary will add the missing information to the statement of the next reporting period, except if the Call for proposals foresees another procedure.

The beneficiary submits to the controller for verification the Table of Expenditure of Annex III in which he/she fills in the relevant data (white parts). He/she also submits all the necessary documents required for the documentation of the realisation of the expenditure and the documents of Chapter 3. The controller is designated according to the provisions of the First Level Control System of the Member State. The controller should verify the soundness of the expenditure declared, the delivery of products and services concerned according to the Application Form and their compliance with the community and national rules according to specific guidelines provided in Chapter 2. The verification should equally ensure that double financing is avoided. The controller confirms the eligible expenditure and does not verify expenditure not documented by the respective supporting documents or not eligible.

When the verification is completed, the controller fills in in the Table of Expenditure the relevant data (grey parts) signs the Certificate of Expenditure and sends these documents to the beneficiary who will, in turn, send them to the lead beneficiary. A copy of these documents is kept on the premises of the beneficiary. The verification of the controller must be finalised within three months from the day of receipt of the request for verification.

The beneficiaries shall send their request for verification preferably on a monthly basis, according to the Programme.

# 3.2. Beneficiary’s supporting documents

In order to verify the expenditure the beneficiary must submit to the controller the supporting documents required in this chapter.

1. Completeness of the folder

- The approved Application Form

- The Subsidy Contract

- The Partnership Agreement

- The Agreement to cooperate, where required

- The regulatory framework of the beneficiary’s operation in force and the legislation the beneficiary follows for recruiting temporary staff or paying its staff additional remuneration.

- The Table of Expenditure of Annex III, filling in accordingly the white parts

- Supporting documents of the expenditure (as described below)

- The necessary documents, as in the Programme Manual, for expenditure declared in a budget line that does not exist in the approved application form, where required

- The necessary documents as in the Programme Manual, for the use of the flexibility rule, where required.

Documents 1- 5 are submitted only during the first request for expenditure verification.

2. Compliance of the expenditure with the project - realisation of the expenditure

- Supporting documents or copies of these e.g. invoices, dispatch notes, discharge notes, payrolls, checks, bank extraits, bank deposit, remittances and other bank documents that document that the expenditure has been realised and paid (reservation on the depreciation). In case expenditure is paid in cash, accounting data of the cashier is provided and the cash movements or the equitable documentation according to the national accounting rules.

- The necessary documents as in the Programme Manual, when there is an amendment in the approved application that the expenditure has been agreed and that the progress of the beneficiary’s work justifies the level of expenditure. The certificate must be original, signed and stamped and it must mention the level of expenditure per budget line.

- Certificates of acceptance of the deliverables by the beneficiary or the lead beneficiary or by the person in charge of the deliverable, in which the part of the deliverable produced by the beneficiary forms part.

- In case the controller is required to verify expenditure where there is no deliverable, e.g. in interim payments to third parties or personnel cost, data from which the declared man-hours are derived, e.g. interim progress reports approved by the beneficiary or the person in charge of the deliverable are submitted.

3. Supporting documents per budget line

3.1 Personnel cost

For the documentation of expenditure of the co funded project paid for personnel cost, the following are submitted:

- Decision of the beneficiary ’s management which specifies the working team, including specific reference to the staff who will work for the project, the division of work, the allocation of working hours, the project manager and the person in charge for accepting the activities/deliverables. The aforementioned could be replaced by employment/labour contracts for each member of the working team which are approved and signed by the responsible body or person according to the institutional framework of the beneficiary.

- Employment/labour contracts and data on the selection procedure (e.g. Call, evaluation, decisions etc) when staff have been hired for the project.

- Decisions of the management regarding the recruitment of staff with reference to the relevant legislation that specifies the recruitment process.

- Monthly timesheets which present the actual hours worked, Annex V, the venue of the work and the nature of the work per employee. These should be signed by the employee, the beneficiary’s responsible and the responsible of the activity.

- Data on the total hours worked per month and date per each employee working on the project, Annex VI, broken down to all the co funded activities/projects he/she has been involved. These are submitted at the end of the value period in printed and electronic version, signed by the employee and validated by the responsible of the beneficiary. The determination of the cost of the shared personnel is conducted based on the actual total time of employment and the total personnel cost of the beneficiary.

- Reports on the produced, by the staff, work during the respective period. The reports should be verified by the responsible of the activity.

- Signed payrolls or payslips or proofs of bank deposits or other supporting documents.

3. 2 Travel ,accommodation and meetings

For the documentation of expenditure of co funded project paid for travel and accommodation the following are submitted:

- Invitation and/or minutes, presenting the time, duration, venue as well as signed list of participants for all the days of the meetings.

- Decision for travelling according to the institutional framework of the beneficiary.

- Travel report/Report on the travel expenditure according to the institutional framework of the beneficiary.

- The beneficiary’s regulation on the level of the subsistence allowances, the kilometre allowance for using private car etc.

- Tickets, invoices of tickets and supporting documents for payments of tickets, toll invoice, invoices of taxi when using taxi or when renting a car or kilometre allowance for using private car when private car is used. In case of travelling by plane, boarding pass is also required.

- The use of taxi or the rent of a car shall be justified when there is no public transport (including strikes etc) or the beneficiary is travelling to subsequent destinations or because it is the most economic way of travelling. In case of insufficient justification the value of the most economic mean of travelling is paid.

- Hotel invoices and supporting documents for hotel payment only for their stay (room service is not included) and for those travelling who should be mentioned by name in the hotel invoice. In case voucher is issued a copy of it should be submitted with the travel agency invoice.

Cost for travelling and accommodation of external experts is paid according to the 	aforementioned rules only when this is explicitly in their contracts.

- Subsistence allowances (only for staff)

- When field work or similar activities are foreseen the programme of field work that the body has approved prior to their commencement shall be submitted, the results of the field work should be kept and should be attached to the travel report.

- In case of travelling outside the eligibility area of the Programme the decisions of the approved bodies of the Programme documenting for these trips.

- In case partners or participants from countries outside the EU travel to the eligible area of the Programme in order to participate to events, justification from the responsible of the beneficiary and the responsible of the activity for their participation.

In case of public procurement for the organisation of workshops, conferences, meetings etc the following are also examined:

- Photographs of workshops, conferences etc

- Contracts and documents for the award procedure (call, tenders, evaluation, decision etc)

- Invoices which should state the project and the Programme

- Certificate of acceptance of products and services

- Documents of payment

The publicity and information documents that address the general public shall respect the rules on publicity of Regulation 1828/2006 (Community emblem, Programme logo, ERDF co funding)

3.4 Publication, information, promotion

For the documentation of expenditure of co funded project paid for publication, information and promotion the following are submitted:

- Contract and documents for the award procedure (call, tenders, evaluation, decision etc)

- Certificate of acceptance of products and services

- Invoices and dispatch notes which should state the project and the Programme

- Documents of payment

- Deliverables of the services offered

- Website of the Programme

- Invitation and agenda

- Minutes

- Singed list of participants

- Photographs of the meeting

The publicity and information documents that address the general public shall respect the rules on publicity of Regulation 1828/2006 (Community emblem, Programme logo, ERDF co financing)

3. 5 Equipment and depreciation

For the documentation of expenditure of co funded projects paid for equipment the following are submitted:

- Contract and documents for the award procedure (call, tenders, evaluation, decision etc)

- Certificate of acceptance of products

- Registration of the equipment in the accounting system according to the national accounting rules (e.g. Register of fixed assets presenting the registration of the equipment)

- Invoices and dispatch notes with reference to the Serial Number of the equipment.

- Documents of payment

- Licenses to set and operate the equipment, where required.

In addition to the aforementioned, for the documentation of depreciation the following are submitted:

- Documentation of the method for depreciation according to the national accounting rules

- Method of partitioning the use of the equipment in the project

3. 6 External experts

For the documentation of expenditure of co funded project paid for external experts the following are submitted:

- Contract and documents for the award procedure (call, tenders, evaluation, decision etc)

- Invoices which they state the project

- Deliverables and certificate of acceptance of deliverables

- Documents of payment

3. 7 Overheads

For the documentation of expenditure of co funded project paid for overheads the following are submitted:

- invoices, receipts and documents of payment

- description of the methodology and the basis for allocation of general costs (where required)

3. 8Public goods and services

For the documentation of expenditure of co funded project paid for public goods and services the following are submitted:

- Contract and documents for the award procedure (call, tenders, evaluation, decision etc)

- Certificate of acceptance of products

- Invoices, contractor’s accounts, summary tables of works

- Documents of payment

- The required by the national legislation licenses (environmental authorisations, permission to set and operate equipment where required)

- In case of public projects implemented in house, diary of works.

4. Compliance with the Regulations publicity rules on documents and deliverables

The beneficiary should respect the provisions of the Regulations on ERDF publicity rules and the Programme publicity rules. It is examined whether the deliverables and the documents bear in a visible part the project logo, the Programme logo, the ERDF co financing and the Community emblem according to the Programme provisions and the provisions of Regulation 1828/2006.

# 3.3 Guidelines for compliance with the public procurement rules

The award of public procurement shall comply with the community and national rules of public procurement as well as with the principles of equal treatment, non discrimination, the obligation for transparency in order to ensure the conditions for the development of real competition at all stages of the procedure.

According to community law the award of public procurement shall be in line with the fundamental principles of the Treaty of the European Communities and the main freedoms of Internal Market. The principles of equal treatment and non discrimination imply the requirement for transparency which is based on a sufficient level of publicity, for the benefit of any potential contractor, in order to allow the opening of the market to competition and the control of the objectivity of the awarding procedures. For contracts with budget which is below the community thresholds as well as for contracts covered by annex IIB of the Regulation 2004/118, irrespectively of budget, a Commission Interpretative Communication  (2006 C/179/02) has been issued on the community law applicable to contract awards not or not fully subject to the provisions of the public procurement dicrectives.

The ECJ, in numerous decisions, has ruled, even in cases of contracts falling out of the scope of the Directive that “the contracting authorities when they conclude them, are bound to respect the fundamental principles of the Treaty generally and the principle of non discrimination on nationality specifically, which implies the obligation of transparency which will allow the contracting authority to be certified for the respect of this principle”

According to the community case law, the obligation of transparency requires a company based on another Member State to have access to appropriate information on the contract prior to its award, in order to, if the company wishes, be in a position to express its interest for the mentioned contract.

In order to achieve respect of the principle of transparency, the foreseen activities on publicity, imply the obligation to explicitly and in a unique way determine the terms and references for participation, the control procedure for the qualitative selection criteria and the evaluation of the award criteria, which makes it unacceptable to amend substantial terms of the call following its publication.

Conducting tendering procedures

In case the total budget of the public procurement is equal or above the thresholds of the Community Directives as in force, the implementation bodies and the beneficiaries shall respect the provisions of the community legislation.

In any case the beneficiaries shall, in every tendering procedure, respect the fundamental principles of the Treaty. Specifically, the procedure and the stages of the tendering procedure shall be explicitly described in the Calls. The following discrete stages shall be described in the structure of the Call:

- Control of the right of participation, i.e.

- Control of the personal situation of the candidate

- Control of the engagement in an occupation, relevant to the tendered project, of the 	candidate

- Control of fulfilling the qualitative selection criteria, i.e.

- Control of technical/occupation skills and/or

- Control of economic/financial adequacy

- Control of the award criteria, i.e.

- Evaluation of the technical offer

- Evaluation of the economic offer

The stages of qualitative selection of the participants and the selection of the contractor for the award of the contract are absolutely discrete and based on different types of criteria. At the stage of control of the right of participation and of the qualitative selection criteria, the criteria are regarding and focus on the contractor, whereas at the stage of the award criteria those are regarding and focus exclusively on the submitted offer.

The technical specifications, i.e. the qualitative characteristics of the works, the financing and the outputs of the contract that shall be achieved shall also be described in detail in the text of the Call. The technical specifications may be demands of different types, e.g. indicatives of quality of production, performance, use, security, methods and ways of implementation, appearance etc. In the framework of the awarding procedure it is recommended, if the following are in accordance with the national law and the provisions of public procurement of the implementing bodies and the beneficiaries, that all supporting documents/certificates possibly required, to be requested only by the temporary contractor and not by all participants, while at the offer submission stage it is recommended that the participation of the candidates is certified with a formal declaration on the fulfillment of the conditions on quality choice (certificate of non-bankruptcy, criminal records, social security and tax declarations etc) as described in the Call. All terms, references and criteria shall be explicitly and in a unique way described in the Calls.

It should be stressed that bodies whose legal entity is of non-profit organization, associations, societies and which are considered as non governmental organizations, although bodies of private law, are required to implement the legislation on public procurement when they participate as beneficiaries or partners of projects of the Operational Programme.

Assurance of non contract splitting of public procurement

According to the provisions on concluding public procurement, the implementation of a project with contract splitting and the award of partial contracts in order to avoid conducting a unique tendering procedure (indicative: international, open, regular etc) of the total budget, is not legal.  The indications and criteria on the existence of contract splitting have been set and specified by the national legislation. Specifically, according to the ECJ case rule the estimation on splitting the budget of the project to individual sections shall be assessed based on the economic and technical function of the outputs of the works included in the contracts (see ruling of C-16/98, Commission vs France)

# Annex I: CONTROL CHECKLIST

- COMPLETENESS OF DATA

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Has the patterned Table of Expenditure been submitted? |  |  |  |  |
| Have the supporting documents been submitted? |  |  |  |  |
| Have the Subsidy Contract and the approved Application form been submitted? |  |  |  |  |
| Has the Partnership Agreement been submitted? |  |  |  |  |
| Is the beneficiary implementing the project the same as the beneficiary of the approved Application Form? |  |  |  |  |
| If the beneficiary implementing the project is not the same as the beneficiary of the approved Application form is there an approved by the Programme Agreement? |  |  |  |  |
| Has the current regulatory framework setting the running of the beneficiary been submitted? |  |  |  |  |
| Has the legislation the beneficiary follows for recruiting temporary staff and for paying additional fees to its staff been submitted? |  |  |  |  |
| Has the certificate from the lead beneficiary that the expenditure not foreseen in the approved application form is agreed been submitted? |  |  |  |  |
| In case of a lead beneficiary: -Is it examined prior to the submission of the financial report if the beneficiaries’ expenditure has been verified by a controller? - Is it examined if the beneficiaries’ controllers verify that the activities have been realised and the respective deliverables been produced according to the Subsidy Contract? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

- COMPLIANCE OF THE EXPENDITURE WITH THE PROJECT –REALISATION OF THE EXPENDITURE

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Has the declared expenditure been included in the Application Form? |  |  |  |  |
| Have costs been correctly allocated to the relevant budget lines? |  |  |  |  |
| Have costs been correctly allocated to the relevant components? |  |  |  |  |
| Has the beneficiary’s budget line and by component as fixed in the approved application form been respected? |  |  |  |  |
| Has all expenditure been incurred and paid within the eligibility period indicated in the subsidy contract? |  |  |  |  |
| Is the existence of deliverables verified by the appropriate certificate of acceptance? |  |  |  |  |
| During the project implementation or after the completion of the project has the beneficiary income been subject to VAT? |  |  |  |  |
| Has refunded VAT been deducted? |  |  |  |  |
| Have any fines and financial penalties been excluded from the expenditure? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

- ACCOUNTING SYSTEM

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Is there a separate accounting unit for the project or have other methods like specific costs centres in the accounting system been established which allow to identify the costs allocated to the project? |  |  |  |  |
| If the beneficiary is required to have an accounting system has he submitted the documents regarding the project (project file, providers)? Specify |  |  |  |  |
| Has each reported expenditure been supported by a paid invoice or an accounting document of equivalent probative value? |  |  |  |  |
| Are the documents complete and accurate in content as well as in accounting terms? |  |  |  |  |
| Is the expenditure recorded in the accounting unit of the project? If not justify . |  |  |  |  |
| Can the amount of the reported expenditure be entirely reconciled with the supporting documents provided? |  |  |  |  |
| Are payments made at the correct amount? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

- DOUBLE FINANCING

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Have rules that ensure the avoidance of double funding been implemented ( e.g. stamping of documents etc)? |  |  |  |  |
| Can it be excluded that expenditure has already been supported by any other funding? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

- ELIGIBILITY OF THE COST

  - STAFF COSTS

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Is there an available list of staff working in the project? |  |  |  |  |
| Is the expenditure only related to employees of the project? |  |  |  |  |
| Are employment contracts available? If yes, which is their type? |  |  |  |  |
| For people working part-time is there a method for calculating the daily/hourly cost available? |  |  |  |  |
| Is the result of the calculation for the aforementioned staff correct? |  |  |  |  |
| Is this calculation for the aforementioned staff based on real worked hours? |  |  |  |  |
| Are there timesheets for each employee per person, month, day with reference to the hours per work package, activity and venue? |  |  |  |  |
| Are they signed by the employee, the beneficiary’s person in charge and the person in charge of the activity? |  |  |  |  |
| Has data of total employment been submitted? |  |  |  |  |
| Are payrolls or payslips or proofs of bank statements or other supporting documents available? |  |  |  |  |
| Is there proof of payment (including social charges) available? |  |  |  |  |
| Have progress reports been submitted? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

  - TRAVEL AND ACCOMMODATION

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Are costs project related? (verify existence of invitation, agenda and/or list of participants) |  |  |  |  |
| Were the trips that these costs refer to justified by the project’s activities as foreseen in the Application Form? |  |  |  |  |
| Are those travelling in the project working team? |  |  |  |  |
| Is there any authorisation of the mission available? |  |  |  |  |
| Is there a travel report signed by the responsible of the beneficiary? |  |  |  |  |
| Are there documents concerning travel and accommodation costs paid directly by the institution available? (Plane tickets, boarding cards, train tickets, hotel invoice, etc.) |  |  |  |  |
| If per diem, is it based on national/institutional rules? |  |  |  |  |
| If real costs, are all supporting documents available? (Meals, transportation, etc.) |  |  |  |  |
| Are the accepted costs levels according to the terms of the call respected? |  |  |  |  |
| Is there travelling by private car? If yes, are there toll invoices, kilometre justification for each destination |  |  |  |  |
| Is there travelling by taxi? Are the specific conditions for the use of taxi respected? |  |  |  |  |
| For any of the expenses, is there proof of payment available? |  |  |  |  |
| In case of trips outside the territory of the Programme, were they explicitly mentioned and justified by the programme bodies prior to its purchase? |  |  |  |  |
| If applicable, are travel and subsistence expenses for third country partners or participants related to events taking place in the Programme territory? |  |  |  |  |
| In case of field work is there an approved by the beneficiary plan for this work? Are there diaries for the results of the field work? |  |  |  |  |
| In case of meetings, are there contracts and the documents of the award procedure? |  |  |  |  |
| In case of meetings has the relevant documentation for the realisation of expenditure been submitted? |  |  |  |  |
| In case of meetings have the minutes, photographs etc been submitted? |  |  |  |  |
| In case of meetings are their certificates of acceptance of goods and services? |  |  |  |  |
| Are payments made against invoices? |  |  |  |  |
| Are invoices sufficiently detailed? |  |  |  |  |
| Is there proof of payment available? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

  - INFORMATION AND PUBLICITY

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Are costs project related? |  |  |  |  |
| Is there a contract laying down the services to be provided? |  |  |  |  |
| Is the acceptance of the contractor’s services certified? |  |  |  |  |
| Are payments made against invoices? |  |  |  |  |
| Are invoices sufficiently detailed? |  |  |  |  |
| Is there proof of payment available? |  |  |  |  |
| Has the beneficiary complied with all relevant rules on European visibility for the selection of the contractor? |  |  |  |  |
| Do all publications or documents produced by the beneficiary comply with the requirements of EC 1828/2006 (inclusion of the EU emblem, a statement that the project was co-financed by the ERDF, the logo of the OP etc) |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

  - EQUIPMENT (DURABLE GOODS)-DEPRECIATION

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Is the equipment purchased stated in the approved application form as in force? |  |  |  |  |
| Is there an inventory of the equipment purchased? |  |  |  |  |
| Has depreciation been applied? |  |  |  |  |
| If applied has the depreciation for the related period been properly calculated by applying national accounting regulations? |  |  |  |  |
| Has the depreciation plan been kept for accounting, control and audit purposes? |  |  |  |  |
| Is it ensured that the items have not already been fully depreciated? |  |  |  |  |
| If not is the late purchase still justified or have the costs been depreciated and only the share corresponding to the remaining project period been reported? |  |  |  |  |
| If the equipment in not exclusively used for project purposes, has only a share of the actual cost been allocated to the project? Is this share calculated according to a fair, justified and equitable method? |  |  |  |  |
| Is there evidence that the equipment has not already been financed by any other funding? (EU, national, regional or other)? |  |  |  |  |
| Was the equipment purchased in compliance with public procurement rules? The public procurement rules depend on the budget level approved to the beneficiary for this category |  |  |  |  |
| Are there contracts and documents for the award procedure? |  |  |  |  |
| Are there the certificates of acceptance? |  |  |  |  |
| In the invoices is the Serial Number stated? |  |  |  |  |
| Is there method for depreciation of the equipment e.g. register of fixed assets presenting the registration of the equipment? |  |  |  |  |
| If required are there licenses for setting and operating the equipment? |  |  |  |  |
| Is there a method partitioning the use of the equipment? |  |  |  |  |
| Are payments made against invoices? |  |  |  |  |
| Are invoices sufficiently detailed? |  |  |  |  |
| Is there proof of payment available? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

  - EXTERNAL EXPERTISE

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Are the contracts of the expenditure controlled foreseen in the approved application form? |  |  |  |  |
| Is it proved that the externalisation was the most appropriate choice? |  |  |  |  |
| Have european and national public procurement rules been respected in the selection process? |  |  |  |  |
| Is there a contract laying down the services provided? |  |  |  |  |
| Are payments made against invoices? |  |  |  |  |
| Are invoices sufficiently detailed? |  |  |  |  |
| Have the services provided by the contractor been accepted? |  |  |  |  |
| Where applicable do the deliverables respect the necessary publicity rules? |  |  |  |  |
| Is there proof of payment available? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

  - PREPARATION COSTS

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Has the beneficiary foreseen preparation costs in the approved application form? |  |  |  |  |
| Have the budget requirements of the call for proposal been respected? |  |  |  |  |
| Have all preparation costs been paid in accordance with the terms of the call for proposals? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

  - OVERHEADS- OPERATIONAL COST (DIRECT OR INDIRECT COST)

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Are there supporting documents justifying all these costs? |  |  |  |  |
| Is there proof of payment available? |  |  |  |  |
| Are overheads (direct or indirect costs) project-related and have not been included in other budget categories? |  |  |  |  |
| In case of indirect case, is there a proof method for allocating overheads to the operation available? |  |  |  |  |
| Is this method duly justified, fair and equitable? |  |  |  |  |
| Has it been properly applied? Is the basis for allocation appropriate? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

  - SERVICES, PUBLIC WORKS

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Are costs project related? |  |  |  |  |
| Is there any evidence that within the beneficiary structure there are no necessary competences nor material means for the provision of the concerned services? |  |  |  |  |
| If this is not case, is it proved that the externalisation was more appropriate? |  |  |  |  |
| Is there a contract laying down the services to be provided? |  |  |  |  |
| Have the serviced provided by the contractor been accepted? |  |  |  |  |
| Are payments made against invoiced? |  |  |  |  |
| Are invoiced sufficiently detailed? |  |  |  |  |
| Is there proof of payment available? |  |  |  |  |
| Are the required studies available? |  |  |  |  |
| Are the required authorisations or discharge available? |  |  |  |  |
| If the implementation of public work is conducted in house is there a diary of work? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

  - OTHER COSTS

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Are these costs mentioned in the approved application form? |  |  |  |  |
| Are these costs supported by invoices or accounting documents of equivalent probative value? |  |  |  |  |
| Is the proof of payment available? |  |  |  |  |
| In case of unpaid voluntary work has the value of that work been determined taking into account the time spent and the hourly and daily rates of remuneration for equivalent work? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

6 COMPLIANCE WITH PUBLIC PROCUREMENT RULES (SERVICES, WORKS, SUPPLIES)

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Have the european and national public procurement rules been respected in the selection process? |  |  |  |  |
| Is the public procurement procedure well documented and documents such as procurement note, terms of reference, offers/quotes, order forms, award decision available? |  |  |  |  |
| Have the principles of transparency, non-discrimination, equal treatment and effective competition been compiled with (also for items below the EU-thresholds)? |  |  |  |  |
| If the beneficiary structure is not subject to the public procurement rules, has a simplified procedure of effective competition been implemented? (Publication on the website of the terms of reference of the services including the weighted criteria of the analysis of the offers) |  |  |  |  |
| In case of tender procedures is the amount of the contract identical to the one stipulated in the offer submitted by the successful tenderer? |  |  |  |  |
| Does the contract contain clauses conflicting with the terms of reference? |  |  |  |  |
| Were the assessment criteria of the offers related to the object of the contract? |  |  |  |  |
| If there have been modifications of the contracts, these comply with Community and national rules? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

7 RESPECT OF OTHER COMMUNITY POLICIES

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| Has the beneficiary complied with all relevant Community rules on the environment? |  |  |  |  |
| Have the results of the environment impact assessment been taken into consideration? |  |  |  |  |
| Has the beneficiary complied with EU objective if promotion of equality? |  |  |  |  |
| Have Community rules on State Aid been respected? Have obligations related to the State Aid discipline been respected? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

8 OTHER CHECKS

| CHECK | YES | NO | N/A | RESULTS/COMMENTS |
| --- | --- | --- | --- | --- |
| If applicable, has the financial analysis according to the provisions of the Programme been submitted? |  |  |  |  |
| Has the administrative check on files been sufficient to gain evidence that the reported activities have taken place, the delivery of services, goods and works are in progress or have been completed? |  |  |  |  |
| INELIGIBLE AMOUNT (If any) |  |  |  |  |

# annex II. CERTIFICATE OF verified expenditure

- OPERATIONAL PROGRAMME:

- PROJECT:

- BENEFICIARY:

- REPORTING PERIOD:

- VERIFICATION: ADMINISTRATIVE

- ON THE SPOT

- CERTIFICATE OF VERIFIED EXPENDITURE

I, the undersigned <full name of controller> hereby certify that all expenditure included in the attached Table of Expenditure have been paid by the beneficiary <full name of beneficiary> for the implementation of the project <project title/acronym> and it is pursuant with:

- The provisions of article 56 of Regulation (EC) No 1083/2006, articles 11 and 13 of Regulation (EC) No 1080/2006 and articles 7, 48 and 53 of Regulation (EC) 1828/2006, as currently applied

- The eligibility criteria of the Operational Programme and the relevant national rules

- The terms of the Subsidy Contract

In particular:

- The certified expenditure has been paid and has been registered in the accounting system of the beneficiary in accordance with the community and national rules within the eligible period;

- The activities (products and services) have been delivered in compliance with the Subsidy Contract and the approved Application form;

- Services, supplies and works have been procured pursuant to the Community public procurement rules and relevant national legislation;

- Irregular expenditure, interest received and revenues have been recovered and deducted from the eligible expenditure;

- There is not any double-financing of the verified expenditure with other community or national schemes and with other programming periods;

- The attached Control Checklist is accurate and is based on reliable accounting evidence and on verifiable documents of equivalent probative value

- The beneficiary has complied with the Community rules and policies regarding publicity, equal opportunities, environmental protection, state aids, competition and public procurement.

- Total certified amount: <0,00> €

(The amount to be certified after any financial corrections and/or deductions settled)

Date: _____________ Place of verification______________________

Full name of controller: ____________________________

- Signature and stamp:  _________________________

- Attached:

- Table of Expenditure

- Control checklist

| Annex III TABLE OF EXPENDITURE. OPERATIONAL PROGRAMME; MONTH (SEMESTER):; YEAR:. PROJECT TITLE (Acronym):; SUNBMISSION BY THE BENEFICIARY - Ref No:. PROJECT ReF No.:; SUNBMISSION BY THE BENEFICIARY - Date:; (dd/mm/yyyy). ROLE OF BENEFICIARY:; FULL NAME OF CONTROLLER and REGISTRATION No.:. BENEFICIARY TITLE & No.:; SUBMISSION TO THE BENEFICIARY - Ref No.:. FULL NAME OF PERSON IN CHARGE OF PARTNER ORGANISATION:; SUBMISSION TO THE BENEFICIARY - Date:; (dd/mm/yyyy). EXPENDITURE OF THE CURRENT PERIOD). Contract ID; Contract Description; TIN; Atteched File. CONTRACTOR'S PAYMENT DETAILS; BENEFICIARY’S PAYMENT DETAILS. Contract ID; WORK PACKAGE No/TITILE; DELIVERABLE No/TITLE; DESCRIPTION OF DELIVERABLES; COST CATEGORY; INVOICE CODE; INVOICE No; DATE OF ISSUE; NET AMOUNT; VAT; INVOICE CODE; INVOICE No; DATE OF ISSUE; NET AMOUNT; VAT; ELIGIBLE COST; COMMENTS. WP…; Deliverable…. Deliverable…. Deliverable…. Deliverable…. WP…; Deliverable…. Deliverable…. Deliverable…. Deliverable…. WP…; Deliverable…. Deliverable…. Deliverable…. Deliverable…. TOTAL; TOTAL. Attachments:. i) Application Form*. ii) Subsidy Contract*; Signature and stamp. iii) Partnership Agreement*. iv) Terms of Reference*. v)Call for Tender*. vi) Contract or equivalent*. vii)Copies of invoices/payslips/bank extre/accounting records. viii) Records/receipts of deliverables. *To be attached only on first submission and re-submitted only if modifications occur. |  |  |  |  |
| --- | --- | --- | --- | --- |

ECJ 342/2008

ECJ 231/2003

ECJ 448/2001