# working document for the rural development committee

August 2015

# Rural Development
Monitoring (2014-2020) – Implementation Report tables

# 1. Introduction

The general approach proposed is that the monitoring data (output indicators and target indicators) are compiled from data items recorded at operation (project) level by the Managing Authority (MA)/ Paying Agency (PA) in the operations database.

The annual monitoring tables will be part of the Annual Implementation Report (AIR) in year N for N-1.

They would include committed expenditure (recorded at approval or application stage) and realised expenditure/outputs (reported at final/annual payment stage for completed operations):

- For the committed data, only expenditure by measure and by focus area (FA) (table A).

- More details (breakdown) for the realised output indicators (tables B and C) would be requested in AIR compared to the indicator plan (breakdown per type of operation, per type of beneficiaries…) in a way to provide more insight on what has been implemented. However, significant effort is made to keep it to the minimum indispensable information.

The value of the target indicators would be provided as at N-1 based on realised outputs/expenditure. In principle, nearly half of the targets can be calculated directly from outputs from table B. The other values would need to be encoded in table D. In table D some outputs are also reported when the applications are approved to provide an early information on the target achievement.

In table E, the total public expenditure is monitored for the transitional measures to show the share of the transitional measures out of the total expenditure (see section on transitional measures).

In table F, mostly generated from tables B, we can monitor the progress made towards the performance framework indicators. An adjustment is necessary if top ups have been taken into account in the target setting (see section on Additional National Financing and State Aid).

In Table B4 (cumulative), the aggregated total public expenditure of all the operations which have been flagged in the operations database for having additional contributions to other FA (other than the FA under which they are programmed and monitored) is indicated. The purpose of this table is to illustrate the multi purpose dimension of operations and, therefore, double counting is possible (see page 7 for further explanations and example).

The annual monitoring tables are cumulative, in a way to best compare to the indicator plan, measuring progress in implementation against the plan (except for area-based measures, when it concerns multi-annual commitments, where cumulative data are more difficult to interpret and for table E). So the monitoring will allow to (cumulatively) compare realised outputs and realised expenditure against the planned outputs and planned expenditure by FA and degree of achievement of the target on an annual basis.

# 2. Structure of the monitoring tables

- Table A: Committed total public expenditure for AIR Year N+1, fed from 2 intermediate tables submitted by 31 October of Year N and 31 January of year N+1

- Tables B:

- B1: Realized output indicators for AIR (cumulative)

- B2: Realized LEADER and TA/Networking output indicators for AIR (cumulative)

- B3: Realized output indicators for multi-annual commitments (annual)

- B4: Total public expenditure of the operations having additional contributions to other FAs (cumulative)

- Table C: Breakdown by NCA area types, type and size of farm holdings supported, gender and age for AIR (cumulative)

- Table D: Progress towards targets for AIR

- Table E: Monitoring of transitional measures (annual)

- Tables F: Progress towards performance framework indicators

# 3. 	general definitions

3.1. Data period and frequency

Table A

According to Article 66 §1 (b) of Regulation (EU) No 1305/2013, the MA provides the Commission 'by 31 January and 31 October in each year of the programme, with relevant indicator data on operations selected for funding, including information on output and financial indicators'. This provision applies to table A.

The following process is envisaged:

| Submission date | Period concerned | Who |
| --- | --- | --- |
| By 31 October Year N | Data from 1 January Year N to 31 August Year N | MA to Commission |
| By 31 January Year N+1 | Data from 1 September Year N to 31 December Year N | MA to Commission |
| Before the submission of the AIR Year N | _ | Commission compiles data at annual level, uploads it in SFC and provides it to MA |
| By 30 June Year N+1 | Year N | Table A covering Year N is available for the AIR Year N. At this stage, in case of administrative errors, corrections could be made. |

Tables B, C, D, E and F

The monitoring data submitted in the AIR must concern the previous calendar year.

These monitoring tables use the calendar year as their framework so all operations realized in YEAR N-1 should be reported (expenditure and output indicators). For example, for AIR submitted by 30 June 2018, the reporting year is 2017.

3.2. Financial data

Financial data concerning the implementation of measures is either expressed as 'committed expenditure' for table A or 'realised expenditure' for other tables.

In the majority of tables financial terms have the following meanings:

- Committed – Total public expenditure (Table A) = Total amount committed (EAFRD + other public) when the application is approved. For multi-annual commitments (e.g. M10 Agri-environment-climate), the commitment is defined annually when the annual claimed expenditure is submitted.

- Realized – Total public expenditure (Tables B1, B2, C and D - Cumulative) = Total amount of expenditure (EAFRD + other public) made by the MS (it should not necessarily have been declared to the Commission) for completed operations in the reporting year and previous years of the programming period.

- Completed operation. Article 2 (14) of Regulation (EU) No 1303/2015 states that a completed operation 'means an operation that has been physically completed or fully implemented and in respect of which all related payments have been made by beneficiaries and the corresponding public contribution has been paid to the beneficiaries. No payments are reported until the operation is completed. Completion is determined by the last payment made (but not necessarily declared to the Commission).

In case of subsidised loans, completion should be determined when the purchase/construction has been physically done. At that moment, all the remaining expenditure of the loan is reported (interest rate subsidy) (in principle this information should be known at that stage).

For multi-annual commitments implemented through annual payments (e.g. M10 Agri-environment-climate), intermediate completion is considered on an annual basis when the claim is paid.

- Realized – Total public expenditure (Table B3 - Annual) = Total amount of expenditure (EAFRD + other public) made by the MS (e.g. area payments not yet necessarily declared to the Commission) for commitments/operations in the reporting year.

- Total investment = sum of all public and private expenditure (eligible expenditure only) of all the tangible and/or intangible investments made for completed operations supported under a particular investment measure/sub-measure. This indicator should only be compiled for investment type of operations.

- Recoveries = in principle recoveries should not be monitored. To be tackled by the financial execution.

- 3.3 Definitions of committed/completed by measures

| Measures | Committed Table A | Realized Tables B1, B2, C |
| --- | --- | --- |
| 1 | Application approved | When operation completed (set of trainings), final payment made |
| 2 | Application approved | Set up farm services: last payment Advices: when operation completed (set of advices), final payment made |
| 4 | Application approved | When operation completed, last payment |
| 5 | Application approved | When operation completed, last payment |
| 6 | Application approved | (6.1 to 6.4): when operation completed, last payment Transfer payment (6.5): one-off: payment completed annual:expenditure are reported on an annual basis when annual payments are made in table B1 (expenditure cumulated) Number of beneficiaries are recorded and reported when the first annual payments are made in table B1 (same beneficiaries should not be double counted over the years) |
| 7 | Application approved | When operation completed, last payment |
| 8.1 and 8.2 Establishment only | Application approved | When operation completed, last payment |
| 8.4 | Application approved | When operation completed, last payment |
| 8.5 | Application approved | When operation completed, last payment |
| 8.6 | Application approved | When operation completed, last payment |
| 16 | Cooperation operations approved | When operation completed, last payment |
| 17.1 | Application approved | Premium paid to beneficiaries |
| 17.2 | Setting up: Mutual fund scheme approved Financial compensation+ costs incurred: / | Setting up of the fund: last payment Financial compensation+ costs incurred: payment made |
| 17.3 | Setting up: Income stabilisation scheme appproved Financial compensation + costs incurred:/ | Setting up of the fund: last payment Financial compensation + costs incurred: payment made |
| 19 | Preparatory works: payment request Running costs, LDS and cooperation projects: when LAG is selected. Unless cooperation projects are selected separately (when selection is approved) | Preparatory works: when payments are made Running cost: payment made When LDS/cooperation operation completed: last payment |
| Measures | Committed - table A | Realized - table B3 |
| 3 | Application approved | Annual payment made |
| 8.1 for maintenance | Commitment signed | Annual payment made |
| 8.2 for maintenance | Commitment signed | Annual payment made |
| 8.3 | Application approved or commitment signed | Annual payment made |
| 9 | Application approved | Annual payment made |
| 10 | Annual payment claimed | Annual payment made during the reporting year Area after on-the-spot checks having received payments |
| 11 | Annual payment claimed | Area after on-the-spot checks having received payments |
| 12 | Annual Payment claimed | Annual payment made |
| 13 | Annual Payment claimed | Annual payment made |
| 14 | Annual Payment claimed | Annual payment made |
| 15 | Annual Payment claimed | Annual payment made |

- 3.4. Other general points

Focus Areas

All the operations should be reported under the FA they belong to. The purpose is to monitor what has been programmed. One operation should not be broken down, the expenditure and output indicators linked to that operation are entirely attributed to the relevant FA.

In general, the FA is known before the implementation of the policy. In the RDP, type of operations or sub-measures have been designed to address specific FA to respond to a need identified and in accordance with the strategy. All the operations supported under these specific sub-measures/type of operations are therefore automatically attributed to the relevant FA in the operations database.

Table B4

In the other tables, the operations are reported under the 'main' FA (or priority for P.4) under which they have been programmed.

On top of that, for each operation approved, the MA should identify in their operations database the FAs to which the operation has additional contributions (if any). The purpose of the Table B4 is to report on that (100% of the total public expenditure of the operation is reported under the FAs to which it has an additional contribution (double counting)). This table is important, notably to monitor the multi-purpose dimension of the rural development operations. Please see example below.

In the first column of Table B4, we have the total public expenditure taken automatically from the other reporting tables (based on the main programmed FA (no double counting)). In the second column, a breakdown for P.4 between FAs 4A, 4B and 4C has to be filled-in. As a consequence of its multi-purpose dimension, P.4 is programmed and monitored at priority level in the other tables and Table B4 is the opportunity to monitor the breakdown between FAs 4A, 4B and 4C (all the operations programmed under P.4  which have contributions to these FAs are reported at 100% under these FAs (double counting).

In the third column, all the operations programmed outside the FA but which have also  additional contributions to that FA are 100% (total public expenditure) reported under that FA. If one operation has additional contributions to several FAs, its total public expenditure will be reported several times (double counting).

On-going commitments from the previous period

In the AIR, ongoing commitments made during the 2007-2013 programming period and supported through 2014-2020 EAFRD and commitments made in 2014 (before the approval of the new RDP) based on the 2007-2013 rules and paid through 2014-2020 EAFRD are monitored in the Tables A, B, C and D. No specific distinction is foreseen.

- The additional Table E allows the monitoring of realized EAFRD and total public expenditure by measure. This table is based on the model of the indicative carry-over table (section 19 of the RDP).

Additional national financing

As Article 82 (Additional National Financing) and Article 81 (State Aid) of Regulation (EU) No 1305/2013 are included in the Indicator Plan for the measures with top ups (taken into account for targets setting, planned expenditure and outputs), the commitments and realisations supported by these articles are also taken into account in the tables. No distinction is foreseen in the Tables A, B, C and D.

Transfer from 1st pillar

First pillar transfers reinforcing certain measures are monitored and included in the monitoring tables (target implementation, realized outputs and expenditure). No distinction is foreseen.

Sub-programme

Targets/outputs and expenditure are monitored in the overall tables aggregated for programme and sub-programme.

In addition, in accordance with Article 75 §3 and §4 of Regulation (EU) No 1305/2013, in the AIR submitted in 2017 and 2019 outputs and targets should be provided for the sub-programme separately, using templates of Tables B and D.

Additional Focus Areas

If an additional FA is programmed, the RDP specific target should be monitored as the other targets. The realized output and expenditure using the common indicators should also be monitored as for any other FA.

Financial Instruments (FI)

In the monitoring tables expenditure and outputs for FI are recorded under the relevant measure (e.g. investment measures 4, 6.4, 7, 8.6 and 16). If both grants and FI are implemented in the same measure and FA, a distinction is requested.

For Table A, the committed expenditure corresponds to the total amount of public contribution (EAFRD and national counterpart) committed in the signed funding agreement (loan, guarantee, equity/quasi-equity or other funds) (codes IV. 16.1.4 + 16.2.1).

For Table B, the realized expenditure corresponds to the total amount of public contribution (EAFRD and national counterpart) actually paid to the FI fund (loan, guarantee, equity/quasi-equity or other funds) on an annual basis (IV. 16.1.4 + 16.2.1).

For the output indicators, as the FI will be implemented through investment measures, the relevant output indicators are:

- Number of operations supported (measures 4, 7 and 8.6: it will correspond to: number of loan contracts signed with final recipient (V. 17.5) + number of final recipients supported by guarantees (V. 18.7) + number of equity or quasi-equity investments made (V. 19.5) + number of other financial product instruments made to final recipient (V. 20.5);

- Number of beneficiaries supported (measures 6.4 and 4.1: it will correspond to: number of final recipients supported by loans (V. 17.6) + number of final recipients supported by guarantees (V. 18.6) + number of final recipients supported by equity or quasi-equity investments (V. 19.6) + number of final recipients supported by other financial product (V. 20.6).

Total investment should not be collected for operations supported through FI.

Only the output for operations supported by EAFRD should be considered.

Currency

All financial amounts must be expressed in Euro (EUR). All figures should be rounded up/down to the nearest whole Euro. If Member States outside the Euro-zone have converted their financial monitoring data from national currencies to Euro, they are requested to indicate the exchange rate they used in the AIR.

4. Output indicators definitions:

O.1 Total public expenditure

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Total amount of expenditure (EAFRD + other public) | All measures | Application form (for commitments), payment claims, PA database of payments Reported when completed |
| For Technical Assistance outside Networking, a breakdown administrative / non-administrative cost is requested. Administrative corresponds to staff costs, office overhead and running costs (see European Court of Auditors Special Report 04/2015). For M04 (4.1, 4.2 and 4.4) and M06 (6.1 to 6.4) operations, a breakdown by type of farm holdings receiving the support (based on FADN TF8 type of agricultural branch + non-agricultural holdings) and size of the farm holdings receiving the support (by hectares) is collected. |  |  |

O.2 Total investment

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Sum of all public and private expenditure (eligible expenditure only) of all the tangible and/or intangible investments made for operations supported under a particular investment measure/sub-measure. | 4, 5, 6.4, 7.2 to 7.8, 8.5 and 8.6 | Application form Reported when completed |
| This indicator should only be compiled for investment type of operations. If no investments are supported, value is NP (not programmed). If no private part is invested such as for 4.4 'non-productive investment' operations, the total investment = total public expenditure. 4, 5, 8.5, 8.6: whole measures. 6: only 6.4 investment in non-agricultural activities in rural areas. 7: whole measure (7.2 to 7.8) except for 7.1 'drawing up and updating plans' . |  |  |

O.3 Number of actions/operations supported

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of operations supported | 1, 2, 4, 6, 7, 8.5 and 8.6, 9, 17.2 and 17.3 | Application form Reported when completed |
| 1: number of actions organized by the service provider broken down by vocational training/skill acquisition; demonstration/information and farm exchange (e.g. One service provider organizing two distinct trainings (one on water management and the other on manure management) = 2 operations, no matter how many times these trainings are provided). 2: number of actions organized by the service provider (2.1 and 2.3) or the body in charge of setting up the service (2.2) broken down by providing advisory services; advisory services set-up and training of advisors (e.g. one service provider organizing two distinct advisory services (one on young farmers business plan and the other on specific agri-environment schemes) = 2 operations, no matter how many times these services are provided). 4: number of investment operations supported (normally it corresponds to the number of applications approved which have been completed) broken down by investments in agricultural holdings (4.1); investments in processing/marketing of agricultural products (4.2); investments in agricultural and forestry infrastructure (4.3) and non-productive investments (4.4); out of which number of operations supported through FI. 6: under FA 5C, this information is notably needed for the common performance framework output indicator. For M04 (4.1, 4.2 and 4.4) and M06 (6.1 to 6.4) operations, a breakdown by type of farm holdings receiving the support (based on FADN TF8 type of agricultural branch + non-agricultural holdings) and size of the farm holdings receiving the support (by hectares) is collected. 7: number of operations (investments, studies or drawing up of plans) supported broken down by operations for drawing up plans of village development (7.1); for drawing up NATURA 2000/HNV area management plans (7.1); for investments of small scale infrastructure, including investments in renewable energy and energy saving (7.2); for investments in broadband infrastructure and access to broadband, including e-government services (7.3); for investments in local basic services for the rural population (7.4); for investments in recreational/tourist infrastructure (7.5); for studies/investments in rural cultural and natural heritage, including HNV sites (7.6); for investments in relocation of activities for environmental/quality of life reasons (7.7); out of which number of operations supported through FI; others (7.8). Particular breakdown for 7.3 (ICT): ICT infrastructure: High-Speed broadband network (access/local loop; >/= 30 Mbps); ICT infrastructure: Very high-speed broadband network (access/local loop; >/= 100 Mbps); ICT: Other types of ICT infrastructure (passive, IT center…); e-Government services. 8.5: number of operations supported. 8.6: number of operations supported, out of which number of operations supported through FI. 9: number of producer groups set up receiving support, reported on an annual basis. 17.2: number of mutual funds supported. 17.3: number of stabilisation tools supported. |  |  |

O.4 Number of holdings/beneficiaries supported

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of holdings/beneficiaries supported | 3.1, 4.1, 5, 6, 8.1 to 8.4, 11, 12, 13, 14, 17.1 | Application form Reported when completed |
| Beneficiaries are individuals or entities other than farm holdings which received support. 3 (only 3.1): number of holdings supported for new participation in quality schemes (broken down by EU schemes, national schemes, voluntary agricultural product certification schemes). For that sub-measure, completion is determined by the annual payment made, reported annually in Table B3 (Article 5 (3) of Regulation (EU) No 215/2014). 4 (only for 4.1): number of holdings supported for investments in agricultural holdings. 5: number of beneficiaries supported for investment in prevention or restoration (broken down by type of beneficiaries: farm holders or others). 6: number of holdings or beneficiaries receiving support (broken down by business start-up aid for young farmers, business start-up aid for non-agricultural activities in rural areas, business start-up aid for development of small farms, support for investments in creation and development of non-agricultural activities, payments for farmers eligible for the small farmers scheme who permanently transfer their holding to another farmer); out of which, number of operations supported through FI. If holdings and beneficiaries are supported under the same sub-measures, they are added up with no distinction. For 6.5, 'small farmers scheme who permanently transfer their holding to another farmer': the number of beneficiaries should not be double counted. In case of annual payment, the beneficiary is reported in the monitoring table when the first annual payment is made. 8.1: number of beneficiaries supported to afforestation/creation of woodland (breakdown maintenance/establishment). For maintenance support, completion is determined by the annual payment made, reported annually in Table B3 (Article 5 (3) of Regulation (EU) No 215/2014). 8.2: number of beneficiaries supported for establishment or maintenance of agro-forestry systems (breakdown maintenance/establishment). For maintenance support, completion is determined by the annual payment made, reported annually in Table B3 (Article 5 (3) of Regulation (EU) No 215/2014). 8.3: number of beneficiaries supported for prevention operations. For that sub-measure, completion is determined by the annual payment made, reported annually in Table B3 (Article 5 (3) of Regulation (EU) No 215/2014). 8.4: number of beneficiaries supported for restoration operations. 11: number of holdings supported through organic farming measure. For that measure, completion is determined by the annual payment made, reported annually in Table B3 (Article 5 (3) of Regulation (EU) No 215/2014). 12: number of holdings supported through NATURA 2000 or Water Framework Directive. For that measure, completion is determined by the annual payment made, reported annually in Table B3 (Article 5 (3) of Regulation (EU) No 215/2014). 13: number of holdings supported through ANC measure. For that measure, completion is determined by the annual payment made, reported annually in Table B3 (Article 5 (3) of Regulation (EU) No 215/2014). 14: number of beneficiaries supported by animal welfare measure. For that measure, completion is determined by the annual payment made, reported annually in Table B3 (Article 5 (3) of Regulation (EU) No 215/2014). 17.1: number of holdings supported for insurance premiums. |  |  |

O.5 Total area (ha)

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Area (ha) : area supported | 4, 8.1 to 8.5, 10.1, 11, 12, 13, 15.1 | IACS/application form/payment claim Reported on an annual basis when annual payments are made except for 8.1 and 8.2 in the case of establishment (operations completed) |
| 4: only area concerned by investments in irrigation under FA 5A – reported when operation is completed. 8.1: area supported broken down by establishment (reported cumulatively) and maintenance (reported on an annual basis). 8.2: area supported broken down by establishment (reported cumulatively) and maintenance (reported on an annual basis). 8.3 and 8.4: area concerned by prevention (reported on an annual basis) and restoration (reported cumulatively). 8.5: area concerned by improving resilience and environmental value of forest ecosystems – reported when operation is completed. 10.1: area under agri-environmental schemes broken down by type of land management (management of inputs including integrated production (reduction of mineral fertilizers, reduction of pesticides); soil cover, ploughing techniques, low tillage, conservation agriculture; reduction of irrigated areas and/or irrigation rate, irrigation techniques; reduction of drainage, management of wetlands; creation, upkeep of ecological features (e.g. field margins, buffer areas, flower strips, hedgerows, trees); maintenance of HNV arable and grassland systems (e.g. mowing techniques, hand labour, leaving of winter stubbles in arable areas), introduction of extensive grazing practices, conversion of arable land to grassland; crop diversification, crop rotation; animal feed regimes, manure management). In case of different schemes of a same measure implemented on the same area, that area is counted several times (no physical area). 11: area supported broken down by conversion and maintenance. 12: area supported broken down by NATURA 2000 agricultural land; NATURA 2000 forestry and Water Framework Directive. 13: area supported broken down by mountain areas; other areas facing natural constraints and others areas affected by specific constraints. 15.1: area supported under forest-environment commitments. In case of different schemes for a same measure implemented on the same area, that area is counted several times (no physical area). |  |  |

O.6 Physical area supported (ha)

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Physical area supported (ha) | 10.1 | IACS/application form Reported on an annual basis |
| 10 (only for 10.1): physical area not broken down neither by type of management nor by FAs (this indicator should not be attributed to FA). The indicator is for the whole RDP, hectares under agri-environment schemes. Schemes implemented under the same area should not be double counted. |  |  |

O.7 Number of contracts supported (ha)

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of contracts supported | 10, 15 | Application form Reported on an annual basis |
| 10: number of contract schemes supported. A farm holder could commit for several contract/schemes broken down by 10.1 and 10.2. 15: number of contract schemes supported. A forestry holder could commit for several contract/schemes. |  |  |

O.8 Number of Livestock Units supported (LU)

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of LU supported | 14, 4 | Application form 4: reported when operation completed 14: reported on an annual basis after annual payment |
| 14: number of LU concerned by the animal welfare commitment supported. 4: only if investments in manure storage/treatment under FA 5D. |  |  |

O.9 Number of holdings participating in supported schemes

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of holdings participating in supported schemes | 9, 16.4, 17.2 and 17.3 | Application form, plus confirmation/amendment on completion of the operation Reported when completed |
| 9 : number of holdings/organisations participating to the producer group supported. For that measure, completion is determined by the annual payment made, reported annually in Table B3 (Article 5 (3) of Regulation (EU) No 215/2014). 16 (only for 16.4): cooperation/local promotion among supply chain actors for establishment and development of short supply chains and local markets. 17.2: number of farm holdings participating in mutual fund supported - reported when completed. 17.3: number of farm holdings participating in stabilisation tool supported – reported when completed. |  |  |

O.10 Number of farmers benefiting from pay-outs

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of farmers benefiting from pay-outs/compensation | 17.2 and 17.3 | Annual reporting to MA from risk management tool manager Reported when completed |
| 17.2: number of farmers receiving pay-outs from the mutual funds. 17.3: number of farmers receiving pay-outs from the stabilisation tool. |  |  |

O.11 Number of training days given

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of training days given | 1.1 | Application form, plus confirmation/amendment on completion of the operation Reported when completed |
| 1 (only 1.1): number of training days given One day equals to 8 hours of training. The indicator is calculated as the sum of the number of hours received by all the participants, divided by 8. |  |  |

O.12 Number of participants  in trainings

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of participants in trainings | 1.1 | Application form, plus confirmation/amendment on completion of the operation Reported when completed |
| 1 (only 1.1): number of participants in trainings It is not necessary to register the identity of participants; the same participant could be counted as many times he/she participates in different trainings. |  |  |

O.13 Number of beneficiaries advised

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of beneficiaries advised | 2.1 | Application form, plus confirmation/amendment on completion of the operation Reported when completed |
| 2 (only 2.1): only for providing advisory services. It is not necessary to register the identity of beneficiaries advised; the same beneficiary could be counted as many times he/she is advised. |  |  |

O.14 Number of advisors trained

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of advisors trained | 2.3 | Application form, plus confirmation/amendment on completion of the operation Reported when completed |
| 2 (only 2.3): number of advisors trained. It is not necessary to register the identity of advisors trained; the same advisor could be counted as many times he/she is trained. |  |  |

O.15 Population benefiting from improved services/infrastructures (IT or others)

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Total population benefiting from improved services/infrastructures (broadband, other ICT or others) | 7 | Application form plus, if needed, confirmation/amendment on completion of operation Reported when completed |
| This output indicator will count the potential population benefiting from improved services/infrastructures via EAFRD operations (breakdown between non-ICT operations (7.1, 7.2 and 7.4 to 7.8), broadband and other ICT). It will count population several times if several operations are supported in the same municipality. However, the target indicators (Table D – see target fiches FA 6B and FA 6A) should count municipalities and related population only once. |  |  |

O.16 Number of EIP groups supported, number of EIP operations supported and number and type of partners in EIP groups

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of EIP operations and type of partners in EIP groups | 16 | Application form Reported when completed |
| Number of EIP groups supported (this indicator should not be attributed to FA, it is measured for the whole RDP). Number of EIP operations supported: some EIP may implement more than one operation (e.g. one operation to promote technologies in the dairy sector and a second operation to test new land practice management to reduce GHG emissions). Each operation will be attributed to the most relevant FA. In general, one operation consists of a set of different actions/operations/projects (seminars, exchanges, researches…). Number of participants to EIP group broken down by type: NGOs, farm holders, research institutes, SMEs, advisors, others (other public bodies…). This indicator should not be attributed to FA. |  |  |

O.17 Number of cooperation operations supported (other than EIP)

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of cooperation operations supported (other than EIP) | 16 | Application form Reported when completed |
| Number of cooperation operations supported (other than EIP) broken down by type: pilot projects, development of new products, processes and technologies (16.2); other co-operation among small operators in organising joint work processes and sharing facilities and resources, and for developing/marketing tourism (16.3); for cooperation on establishment and development of short supply chains / local markets or for local promotion of short supply chains and local markets (16.4); for joint action to mitigate or adapt to climate change or for collective approaches to environmental projects/practices (16.5); for co-operation among supply chain actors for sustainable provision of biomass (16.6); for non-CLLD local development strategies (16.7); for the drawing up of forest management plans (16.8); diversification of farming activities into activities concerning health care, social integration, community-supported agriculture and education about the environment and food (16.9); others (16.10). One operation could either equal to one project (e.g. drawing up of forest management plan) or not (e.g. non-CLLD local strategies…). For certain, one operation supported (group, network/cluster, non-CLLD local strategies …) would probably implement several projects. |  |  |

O.18 Population covered by LAG

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Population covered by LAG | 19 | MA/LAG Reported when LAG selected |
| See target fiche for FA 6B (this indicator should not be attributed to FA) |  |  |

O.19 Identification number of LAG

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Identification number of LAG | 19 | MA Reported when LAG selected |
| Total number of LAGs selected and number of LAGs multi-funds (this indicator should not be attributed to FA). |  |  |

O.20 Number of LEADER projects suported

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of LEADER projects supported | 19 | Application, reporting from LAG manager Reported when completed |
| For each project, the LAG managers identify what is the main objective of the project (by using the list of FA, the project is flagged with the most relevant FA). To monitor the contributions of the LEADER projects to the FAs, one indicator per project is collected. The indicator to be collected depends on the main FA the project contributes to. List of indicators to be collected depending on the most relevant objective of the LEADER project: 1A; -. 1B; Number of cooperation operations (non-Article 35 §1c) of Regulation (EU) No 1303/2013 operations). 1C; Number of participants trained. 2A, 2B; Number of holdings/beneficiaries supported. 3A, 3B; Number of holdings supported or participating in supported schemes. 4A, 4B, 4C; Total area (agriculture). 4A, 4B, 4C; Total area (forestry). 5A; Total area. 5B, 5C; Total investment. 5D; Total area or number of LU. 5E; Total area. 6A; -. 6B; Population benefiting from improved services/infrastructures. 6C; Population benefiting from improved ICT services/infrastructures. |

O.21 Number of cooperation projects supported

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of cooperation projects supported | 19 | Application, reporting from LAG Reported when completed |
| Number of cooperation projects supported broken down by inter-territorial cooperation and transnational cooperation (this indicator should not be attributed to FA). |  |  |

O.22 Number and type of project promoters

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number and type of project promoters | 19 | Application, reporting from LAG Reported when completed |
| Number and type of project promoters broken down by NGOs, LAGs, public bodies, SMEs, others (this indicator should not be attributed to FA). |  |  |

O.23 Unique identification number of LAG involved in cooperation projects

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Unique number of LAG involved in cooperation projects | 19 | MA, reporting from LAG Reported when completed |
| Unique number of LAG involved in cooperation projects supported, broken down by inter-territorial cooperation and transnational cooperation (this indicator should not be attributed to FA). |  |  |

O.24 Number of thematic and analytical exchanges set up with the support of NRN

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of thematic and analytical exchanges set up with the support of NRN, by type | Networking | NRN reporting to MA annually Reported when completed |
| This indicator counts the total number of thematic and analytical exchanges set up broken down by: - Number of thematic working groups set up; - Number of consultations (e.g. between MA and NRN stakeholders on programme modifications…); - Others (trainings, web forum…). Out of these total number of thematic and analytical exchanges set up, it is counted how many: - Are focused on sharing and disseminating monitoring and evaluation findings; - Are devoted to advisors and/or innovation support services; - Are devoted to LAG including support to cooperation. |  |  |

O.25 Number of NRN communication tools

| Title and definition | Measures concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of NRN communication tools, by type | Networking | NRN reporting to MA annually Reported when completed |
| This indicator is broken down as follows: - Total events organized (seminars, conference, field trips….); - Number of publications: leaflets, newsletters, magazines… issued by the NRN including e-publications; - Number of other NRN communication tools used to communicate RDP to broader public (e.g. website, social media....); - Number of project examples collected and dissiminated by NRN; From project databases, number of projects identified, collected, documented and disssimated. Out of these total number of events organized, publications and other communication tools, it is counted how many: - Are focused on sharing and disseminating monitoring and evaluation findings; - Are devoted to advisors and/or innovation support services; - Are devoted to LAG including support to cooperation. |  |  |

O.26 Number of ENRD activities in which the NRN has participated

| Title and definition | Measure concerned | Source of data, timing of reporting |
| --- | --- | --- |
| Number of ENRD activities in which the NRN has participated | Networking | NRN reporting to MA annually Reported when completed |
| This indicator counts all ENRD activities in which the NRN has participated and out of those to which the NRN actively contributed (e.g. through presentations, facilitation of working groups, poster sessions, etc.). |  |  |

List and definitions of pre-defined output indicators used for the performance framework

These indicators are pre-calculated by SFC 2014 based on the Indicator Plan. The output indicators can be adapted/changed by the MA to better represent the RDP specificities.

|  | Indicators | Definitions of the pre-defined performance framework indicators |
| --- | --- | --- |
| Priority 2 | Total Public Expenditure P2 (€) | ∑ of total public expenditure of all measures under P2 |
|  | Number of agriculture holdings with RDP support for investment in restructuring or modernisation (2A) + Number of agricultural holdings with RDP supported business development plan/investment for young farmers (2B) | Number of holdings supported under 4.1 (2A) + number of holdings supported under 6.1 (2B) {or number of holdings supported under 4.1 (2B) if 6.1 = 0 } |
| Priority 3 | Total Public Expenditure P3 (€) | ∑ of total public expenditure of all measures under P3 |
|  | Nr of agricultural holdings supported under quality schemes, local markets/short supply circuits, and producer groups (3A) | Number of holdings supported under 3.1 (3A) + Number of holdings supported under 9 (3A) + Number of holdings supported under 16.4 (3A) |
|  | Number of agricultural holdings participating in risk management schemes (3B) | Number of holdings supported under 17.1 (3B) + Number of holdings participating in 17.2 (3B) + Number of holdings participating in 17.3 (3B) + number of holdings supported for preventive actions 5.1 (3B) |
| Priority 4 | Total Public Expenditure P4 (€) | ∑ of total public expenditure of all measures under P4 |
|  | Agricultural land under management contracts contributing to biodiversity (ha) (4A) + Agricultural land under management contracts improving water management (ha) (4B) + Agricultural land under management contracts improving soil management and/preventing soil erosion (ha) (4C) | Total area supported under 8.1 (P4 Ag) + Total area supported under 8.2 (P4 Ag) + Total area supported under 10.1 (P4 Ag) + Total area supported under 11.1 (P4 Ag) + Total area supported under 11.2 (P4 Ag) + Total area supported under 12.1 (P4 Ag) + Total area supported under 12.3 (P4 Ag) |
| Priority 5 | Total Public Expenditure P5 (€) | ∑ of total public expenditure of all measures under P5 |
|  | Nr of investment operations in energy savings and efficiency (€) (5B) + Nr of investment operations in renewable energy production (€) (5C) | Number of operations supported under 4.1 to 4.3 (5B) + Number of operations supported under 7.2 (5B) + Number of operations supported under 4.1 to 4.3 (5C) + Number of operations supported under 7.2 (5C) +Number of operations supported under 6 (5C) + Number of operations supported under 8.6 (5C) + |
|  | Agricultural and forest land under management to foster carbon sequestration/conservation (ha) (5E) + Agricultural land under management contracts targeting reduction of GHG and/or ammonia emissions (ha) (5D) + Irrigated land switching to more efficient irrigation system (ha) (5A) | Total area supported under 10.1 (5A) + Total area supported under 4 (5A) + Total area supported under 10.1 (5D) + Total area supported under 10.1 (5E) + Total area supported under 8.1 (5E) + Total area supported under 8.2 (5E) |
| Priority 6 | Total Public Expenditure P6 (€) | ∑ of total public expenditure of all measures under P6 |
|  | Nr of operations supported to improve basic services and infrastructures in rural areas (6B and 6C) | Number of operations supported under 7 (6B) + Number of operations supported under 7.3 (6C) |
|  | Population covered by LAG | Population covered by LAG |

Table A: Committed expenditure (Article 66 §1 (b) of Regulation (EU) No 1305/2013 - Indicator data provision)

Table B1 - Table with realised outputs (AIR) - CUMULATIVE

Table B2 - Table with realised LEADER and TA/Networking outputs (AIR) – CUMULATIVE

Table B3 - Table with realised output indicators for area-based, LU and multi-annual measures (AIR) - ANNUAL

Table B4 - Total public expenditure of the operations which have additional contributions to other Focus Areas (AIR) - CUMULATIVE

Table C: Breakdown by gender, type of agricultural branch and size, age and area type - Cumulative

Table D: Progress towards target

Table E: Monitoring of total public expenditure for transitional measures - ANNUAL

Table F (AIR): Progress towards performance framework indicators (using pre-defined output indicators, to be adapted depending on the RDP)

|  | Indicators | Realised performance framework indicators (Year N)* | Adjustment top ups | Calculated achievement rate (YEAR N)** | Milestones | Targets 2023 |
| --- | --- | --- | --- | --- | --- | --- |
| Priority 2 | Total Public Expenditure P2 (€) |  |  |  |  |  |
|  | Number of agriculture holdings with RDP support for investment in restructuring or modernisation (2A) + Number of agricultural holdings with RDP supported business development plan/investment for young farmers (2B) |  |  |  |  |  |
| Priority 3 | Total Public Expenditure P3 (€) |  |  |  |  |  |
|  | Nr of agricultural holdings supported under quality schemes, local markets/short supply circuits, and producer groups (3A) |  |  |  |  |  |
|  | Number of agricultural holdings participating in risk management schemes (3B) |  |  |  |  |  |
| Priority 4 | Total Public Expenditure P4 (€) |  |  |  |  |  |
|  | Agricultural land under management contracts contributing to biodiversity (ha) (4A) + Agricultural land under management contracts improving water management (ha) (4B) + Agricultural land under management contracts improving soil management and/preventing soil erosion (ha) (4C) |  |  |  |  |  |
| Priority 5 | Total Public Expenditure P5 (€) |  |  |  |  |  |
|  | Nr of investment operations in energy savings and efficiency (€) (5B) + Nr of investment operations in renewable energy production (€) (5C) |  |  |  |  |  |
|  | Agricultural and forest land under management to foster carbon sequestration/conservation (ha) (5E) + Agricultural land under management contracts targeting reduction of GHG and/or ammonia emissions (ha) (5D) + Irrigated land switching to more efficient irrigation system (ha) (5A) |  |  |  |  |  |
| Priority 6 | Total Public Expenditure P6 (€) |  |  |  |  |  |
|  | Nr of operations supported to improve basic services and infrastructures in rural areas (6B and 6C) |  |  |  |  |  |
|  | Population covered by LAG |  |  |  |  |  |

*: data generated from tables B and D of the AIR

**: ratio calculated based on targets set in the RDP

First AIR 2016 covers 2 calendar years: 2014 and 2015.

In tables D, some outputs are also reported when the operations are approved.

According to Article 2 (15) of Regulation (EU) No 1303/2015: "public expenditure means any public contribution to the financing of operations the source of which is the budget of national, regional or local public authorities, the budget of the Union related to the ESI Funds, the budget of public law bodies or the budget of associations of public authorities or of public law bodies (…)".

See Fiche 4B Monitoring of Financial Instruments and provision of monitoring information to the Commission

“Area” relates to the total area under each type of contract, i.e. a hectare subject to two separate agri-environment contracts is counted twice.

"Physical area supported" is the actual area covered by contracts, i.e. each hectare is only counted once, regardless of how many separate contracts it may be subject to.